## Report
■ Monthly Progress Report (Onboard Equipment Installation) | [12 empty] | Updated : | 2016-09-24
NO | Operator (Depot) | Agency | Phase | Category | Q'ty |  |  | 2016 | [5 empty] | Remark
|  | Sub Agency |  |  | Total Plan | Total Actual |  | 7 | 8 | 9 | 10 | 11 | 12
[5 empty] | Q'ty | Q'ty | Progress
SUM |  |  |  | Cabling | 615 | 501 | 81.46% | 236 | 208 | 57 | 0 | 0 | 0
|  |  |  | Equipment Installation | 615 | 354 | 57.56% | 0 | 99 | 255 | 0 | 0 | 0
|  |  |  | IC Confirm | 615 | 65 | 10.57% | 0 | 6 | 59 | 0 | 0 | 0
1 | VOTANIKOS | OSY | P2 | Cabling | 227 | 194 | 85.46% | 180 | 14 | 0 | 0 | 0 | 0
|  | Thermal Bus |  | Equipment Installation | 227 | 192 | 84.58% | 0 | 87 | 105 | 0 | 0 | 0
|  |  |  | IC Confirm | 227 | 65 | 28.63% | 0 | 6 | 59 | 0 | 0 | 0
2 | ELLINIKO | OSY |  | Cabling | 0 | 1 | #DIV/0! | 0 | 1 | 0 | 0 | 0 | 0
|  | Thermal Bus |  | Equipment Installation | 0 | 1 | #DIV/0! | 0 | 1 | 0 | 0 | 0 | 0
|  |  |  | IC Confirm | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
3 | RENTI | OSY | P2 | Cabling | 275 | 240 | 87.27% | 56 | 183 | 1 | 0 | 0 | 0
|  | Thermal Bus |  | Equipment Installation | 275 | 95 | 34.55% | 0 | 1 | 94 | 0 | 0 | 0
|  |  |  | IC Confirm | 275 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
4 | PETROU RALLI | OSY |  | Cabling | 0 | 2 | #DIV/0! | 0 | 2 | 0 | 0 | 0 | 0
|  | Thermal Bus |  | Equipment Installation | 0 | 2 | #DIV/0! | 0 | 2 | 0 | 0 | 0 | 0
|  |  |  | IC Confirm | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
5 | AGIO DIMITRIOS | OSY |  | Cabling | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
|  | Thermal Bus |  | Equipment Installation | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | IC Confirm | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
6 | ANTHOUSA | OSY |  | Cabling | 0 | 2 | #DIV/0! | 0 | 2 | 0 | 0 | 0 | 0
|  | Thermal Bus |  | Equipment Installation | 0 | 2 | #DIV/0! | 0 | 2 | 0 | 0 | 0 | 0
|  |  |  | IC Confirm | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
7 | ANO LIOSIA | OSY |  | Cabling | 0 | 1 | #DIV/0! | 0 | 1 | 0 | 0 | 0 | 0
|  | Thermal Bus |  | Equipment Installation | 0 | 1 | #DIV/0! | 0 | 1 | 0 | 0 | 0 | 0
|  |  |  | IC Confirm | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
8 | NEA FILADELFIA | OSY |  | Cabling | 0 | 2 | #DIV/0! | 0 | 2 | 0 | 0 | 0 | 0
|  | Trolley Bus |  | Equipment Installation | 0 | 2 | #DIV/0! | 0 | 2 | 0 | 0 | 0 | 0
|  |  |  | IC Confirm | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0
9 | ATTIKI | OSY | P2 | Cabling | 29 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  | Trolley Bus |  | Equipment Installation | 29 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | IC Confirm | 29 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
10 | ROUF | OSY | P2 | Cabling | 69 | 56 | 81.16% | 0 | 2 | 54 | 0 | 0 | 0
|  | Trolley Bus |  | Equipment Installation | 69 | 56 | 81.16% | 0 | 2 | 54 | 0 | 0 | 0
|  |  |  | IC Confirm | 69 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
11 | TRAM (ELLINIKO) | STASY | P2 | Cabling | 15 | 3 | 20% | 0 | 1 | 2 | 0 | 0 | 0
|  | TRAM |  | Equipment Installation | 15 | 3 | 20% | 0 | 1 | 2 | 0 | 0 | 0
|  |  |  | IC Confirm | 15 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0
Note on G7: njcho: Pilot (8)buses not included
Note on I7: njcho: Pilot 8 buses included

## Install
■ Install List (Onboard Installation) for Thermal Bus
| Updated |  | 24.09.16
[8 empty] | 501 |  |  |  | 354 | 980 | [17 empty] | 357 |  |  |  | 357
NO | Basic Info |  |  |  | Cabling |  |  |  | Equipment Install |  |  |  | Equipment | [23 empty] | IC Confirm |  |  | Remark
| Vehicle ID | Plate No | Depot | Model of Vehicle | Plan |  | Actual |  | Plan |  | Actual |  | OSCVM-1 |  |  | OSCVM-2 |  |  | OSCVM-3 |  |  | OSCVM-4 |  |  | OSCVM-5 |  |  | OSCVM-6 |  |  | OVMC-1 |  | OVMC-2 |  | OBCH-1 | OBCH-2 | Plan | Actual
[5 empty] | Start | End | Start | End | Start | End | Start | End | Device ID | S/N | PSAM | Device ID | S/N | PSAM | Device ID | S/N | PSAM | Device ID | S/N | PSAM | Device ID | S/N | PSAM | Device ID | S/N | PSAM | Device ID | S/N | Device ID | S/N | S/N | S/N |  |  | PIN_Fixed
1 |  | ΥΕΚ 5247 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-11 | 2016-07-11 | [30 empty] | X
2 | 1000000003 | ΥΕΚ 5250 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-11 | 2016-07-11 |  |  | 2016-08-23 | 2016-08-23 |  | 160001891625 |  |  | 160003341625 |  |  | 160004951625 | [11 empty] | 162001681625 |  |  | 155000571624 |  | 2016-09-10 | 2016-09-10 | X
3 | 1000000020 | ΥΕΚ 5270 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-11 | 2016-07-11 |  |  | 2016-08-29 | 2016-08-29 |  | 160002081625 |  |  | 160004781625 |  |  | 160001521625 | [11 empty] | 162000801625 |  |  | 155001981624 |  |  |  | X
4 | 1000000009 | ΥΕΚ 5257 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-11 | 2016-07-11 |  |  | 2016-08-24 | 2016-08-24 |  | 160005781625 |  |  | 160000231625 |  |  | 160003391625 | [11 empty] | 162001221625 |  |  | 155000671624 |  | 2016-08-27 | 2016-08-27 | X
5 | 1000000016 | ΥΕΚ 5266 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-11 | 2016-07-11 |  |  | 2016-08-26 | 2016-08-26 |  | 160004731625 |  |  | 160004881625 |  |  | 160001791625 | [11 empty] | 162001901625 |  |  | 155002181624 |  |  |  | X
6 | 1000000012 | ΥΕΚ 5261 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-11 | 2016-07-11 |  |  | 2016-08-24 | 2016-08-24 |  | 160002581625 |  |  | 160000671625 |  |  | 160000251625 | [11 empty] | 162000791625 |  |  | 155001121624 |  |  |  | X
7 | 1000000006 | ΥΕΚ 5254 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-11 | 2016-07-11 |  |  | 2016-08-23 | 2016-08-23 |  | 160003751625 |  |  | 160001191625 |  |  | 160001371625 | [11 empty] | 162002091625 |  |  | 155001111624 |  | 2016-08-27 | 2016-08-27 | X
8 | 1000000021 | ΥΕΚ 5271 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-11 | 2016-07-11 |  |  | 2016-08-29 | 2016-08-29 |  | 160002691625 |  |  | 160004811625 |  |  | 160003171625 | [11 empty] | 162000971625 |  |  | 155000821624 |  | 2016-09-03 | 2016-09-03 | X
9 | 1000000018 | ΥΕΚ 5268 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-11 | 2016-07-11 |  |  | 2016-08-27 | 2016-08-27 |  | 160003451625 |  |  | 160000761625 |  |  | 160005361625 | [11 empty] | 162000211625 |  |  | 155001621624 |  |  |  | X
10 | 1000000022 | ΥΕΚ 5272 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-11 | 2016-07-11 |  |  | 2016-08-30 | 2016-08-30 |  | 160004161625 |  |  | 160002141625 |  |  | 160004751625 | [11 empty] | 162001731625 |  |  | 155001491624 |  | 2016-09-03 | 2016-09-03 | X
11 | 1000000015 | ΥΕΚ 5264 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-11 | 2016-07-11 |  |  | 2016-08-26 | 2016-08-26 |  | 160000571625 |  |  | 160002111625 |  |  | 160002721625 | [11 empty] | 162001941625 |  |  | 155001691624 |  |  |  | X
12 | 1000000024 | ΥΕΚ 5275 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-12 | 2016-07-12 |  |  | 2016-08-30 | 2016-08-30 |  | 160003311625 |  |  | 160004401625 |  |  | 160003211625 | [11 empty] | 162000421625 |  |  | 155001481624 |  |  |  | X
13 | 1000000026 | ΥΕΚ 5277 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-12 | 2016-07-12 |  |  | 2016-08-30 | 2016-08-30 |  | 160005601625 |  |  | 160003301625 |  |  | 160005891625 | [11 empty] | 162000181625 |  |  | 155001791624 |  |  |  | X
14 | 1000000025 | ΥΕΚ 5276 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-12 | 2016-07-12 |  |  | 2016-08-31 | 2016-08-31 |  | 160003951625 |  |  | 160005691625 |  |  | 160005761625 | [11 empty] | 162000751625 |  |  | 155002431624 |  |  |  | X
15 | 1000000010 | ΥΕΚ 5258 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-12 | 2016-07-12 |  |  | 2016-08-25 | 2016-08-25 |  | 160002851625 |  |  | 160000621625 |  |  | 160006051626 | [11 empty] | 162000671625 |  |  | 155001291624 |  |  |  | X
16 | 1000000023 | ΥΕΚ 5274 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-12 | 2016-07-12 |  |  | 2016-08-31 | 2016-08-31 |  | 160000981625 |  |  | 160004301625 |  |  | 160004851625 | [11 empty] | 162000481625 |  |  | 155002471624 |  | 2016-09-03 | 2016-09-03 | X
17 |  | ΥΝΝ 9686 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-12 | 2016-07-12 | [30 empty] | X
18 | 1000000163 | ΥΝΝ 9682 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-12 | 2016-07-12 |  |  | 2016-08-23 | 2016-08-23 |  | 160003971625 |  |  | 160002281625 | [14 empty] | 162000721625 |  |  | 155001281624 |  |  |  | X
19 | 1000000165 | ΥΝΝ 9684 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-12 | 2016-07-12 |  |  | 2016-08-24 | 2016-08-24 |  | 160001311625 |  |  | 160002021625 | [14 empty] | 162001051625 |  |  | 155001511624 |  | 2016-08-27 | 2016-08-27 | X
20 | 1000000171 | ΥΝΝ 9691 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-12 | 2016-07-12 |  |  | 2016-08-23 | 2016-08-23 |  | 160005731625 |  |  | 160004231625 | [14 empty] | 162001871625 |  |  | 155001001624 |  | 2016-09-03 | 2016-09-03 | X
21 | 1000000168 | ΥΝΝ 9687 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-12 | 2016-07-12 |  |  | 2016-08-25 | 2016-08-25 |  | 160004051625 |  |  | 160004011625 | [14 empty] | 162001281625 |  |  | 155002701625 |  | 2016-09-10 | 2016-09-10 | X
22 | 1000000230 | ΥΝΝ 9755 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-12 | 2016-07-12 |  |  | 2016-09-02 | 2016-09-02 |  | 160002161625 |  |  | 160000801625 | [14 empty] | 162005461632 |  |  | 155002231624 |  |  |  | X
23 | 1000000169 | ΥΝΝ 9688 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-12 | 2016-07-12 |  |  | 2016-08-23 | 2016-08-23 |  | 160004541625 |  |  | 160002471625 | [14 empty] | 162001611625 |  |  | 155002081624 |  | 2016-09-10 | 2016-09-10 | X
24 | 1000000174 | ΥΝΝ 9696 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-13 | 2016-07-13 |  |  | 2016-08-24 | 2016-08-24 |  | 160005681625 |  |  | 160004411625 | [14 empty] | 162001651625 |  |  | 155002141624 |  | 2016-09-03 | 2016-09-03 | X
25 | 1000000178 | ΥΝΝ 9700 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-13 | 2016-07-13 |  |  | 2016-08-25 | 2016-08-25 |  | 160004831625 |  |  | 160005631625 | [14 empty] | 162001481625 |  |  | 155002771625 |  | 2016-09-03 | 2016-09-03 | X
26 | 1000000175 | ΥΝΝ 9697 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-13 | 2016-07-13 |  |  | 2016-08-24 | 2016-08-24 |  | 160000741625 |  |  | 160000481625 | [14 empty] | 162001191625 |  |  | 155001341624 |  | 2016-09-03 | 2016-09-03 | X
27 | 1000000177 | ΥΝΝ 9699 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-13 | 2016-07-13 |  |  | 2016-09-09 | 2016-09-09 |  | 160002341625 |  |  | 160020051633 | [14 empty] | 162006081632 |  |  | 155003181630 |  |  |  | X
28 | 1000000176 | ΥΝΝ 9698 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-13 | 2016-07-13 |  |  | 2016-08-24 | 2016-08-24 |  | 160000471625 |  |  | 160005961625 | [14 empty] | 162001411625 |  |  | 155000651624 |  | 2016-09-10 | 2016-09-10 | X
29 | 1000000173 | ΥΝΝ 9694 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-13 | 2016-07-13 |  |  | 2016-08-27 | 2016-08-27 |  | 160002681625 |  |  | 160003491625 | [14 empty] | 162000361625 |  |  | 155002281624 |  | 2016-09-03 | 2016-09-03 | X
30 |  | ZKZ 9827 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-13 | 2016-07-13 | [30 empty] | X
31 | 1000000598 | ZKZ 9705 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-13 | 2016-07-13 |  |  | 2016-09-12 | 2016-09-12 |  | 160000841625 |  |  | 160004801625 |  |  | 160014291632 | [11 empty] | 162002001625 |  |  | 155003671630 |  |  |  | O
32 | 1000000017 | ΥΕΚ 5267 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-13 | 2016-07-13 |  |  | 2016-08-27 | 2016-08-27 |  | 160002011625 |  |  | 160003631625 |  |  | 160005771625 | [11 empty] | 162000931625 |  |  | 155002641625 |  |  |  | X
33 | 1000000027 | ΥΕΚ 5278 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-13 | 2016-07-13 |  |  | 2016-08-31 | 2016-08-31 |  | 160000461625 |  |  | 160002701625 |  |  | 160003591625 | [11 empty] | 162000731625 |  |  | 155002331624 |  | 2016-09-03 | 2016-09-03 | X
34 | 1000000013 | ΥΕΚ 5262 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-13 | 2016-07-13 |  |  | 2016-08-24 | 2016-08-24 |  | 160003251625 |  |  | 160005181625 |  |  | 160004721625 | [11 empty] | 162001711625 |  |  | 155000691624 |  |  |  | X
35 | 1000000030 | ΥΕΚ 5282 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-13 | 2016-07-13 |  |  | 2016-09-10 | 2016-09-10 |  | 160020651633 |  |  | 160001671625 |  |  | 160002271625 | [11 empty] | 162004281630 |  |  | 155004141630 |  |  |  | O
36 | 1000000028 | ΥΕΚ 5279 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-13 | 2016-07-13 |  |  | 2016-09-06 | 2016-09-06 |  | 160007071630 |  |  | 160018751633 |  |  | 160019621633 | [11 empty] | 162003951630 |  |  | 155001301624 |  |  |  | X
37 | 1000000594 | ZKZ 9701 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-13 | 2016-07-13 |  |  | 2016-09-12 | 2016-09-12 |  | 160001611625 |  |  | 160004361625 |  |  | 160002201625 | [11 empty] | 162001391625 |  |  | 155004851630 |  |  |  | O
38 | 1000000183 | ΥΝΝ 9705 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-14 | 2016-07-14 |  |  | 2016-08-26 | 2016-08-26 |  | 160001281625 |  |  | 160001041625 | [14 empty] | 162001151625 |  |  | 155000721624 |  | 2016-09-03 | 2016-09-03 | X
39 | 1000000184 | ΥΝΝ 9706 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-14 | 2016-07-14 |  |  | 2016-08-25 | 2016-08-25 |  | 160003381625 |  |  | 160003191625 | [14 empty] | 162000501625 |  |  | 155001701624 |  | 2016-09-03 | 2016-09-03 | X
40 | 1000000185 | ΥΝΝ 9707 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-14 | 2016-07-14 |  |  | 2016-08-26 | 2016-08-26 |  | 160002821625 |  |  | 160004131625 | [14 empty] | 162002161625 |  |  | 155002721625 |  | 2016-09-03 | 2016-09-03 | X
41 | 1000000186 | ΥΝΝ 9708 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-14 | 2016-07-14 |  |  | 2016-08-26 | 2016-08-26 |  | 160003001625 |  |  | 160000541625 | [14 empty] | 162000441625 |  |  | 155002021624 |  | 2016-09-03 | 2016-09-03 | X
42 | 1000000187 | ΥΝΝ 9709 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-14 | 2016-07-14 |  |  | 2016-08-27 | 2016-08-27 |  | 160000631625 |  |  | 160001381625 | [14 empty] | 162001371625 |  |  | 155002841626 |  | 2016-09-03 | 2016-09-03 | X
43 | 1000000188 | ΥΝΝ 9710 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-14 | 2016-07-14 |  |  | 2016-09-08 | 2016-09-08 |  | 160007901630 |  |  | 160019331633 | [14 empty] | 162001471625 |  |  | 155000741624 |  | 2016-09-10 | 2016-09-10 | X
44 | 1000000189 | ΥΝΝ 9711 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-14 | 2016-07-14 |  |  | 2016-08-29 | 2016-08-29 |  | 160003981625 |  |  | 160006021625 | [14 empty] | 162001991625 |  |  | 155000841624 |  | 2016-09-10 | 2016-09-10 | X
45 | 1000000078 | ΥMI 1553 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-14 | 2016-07-14 |  |  | 2016-08-27 | 2016-08-27 |  | 160003931625 |  |  | 160003181625 |  |  | 160001531625 | [11 empty] | 162001581625 |  |  | 155001841624 |  | 2016-09-03 | 2016-09-03 | X
46 | X | ΥMI 1555 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-14 | 2016-07-14 |  |  | 2016-09-09 | 2016-09-09 |  | 160021271633 |  |  | 160000781625 |  |  | 160004681625 | [11 empty] | 162000981625 |  |  | 155002861630 |  |  |  | X
47 | 1000000080 | ΥMI 1556 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-14 | 2016-07-14 |  |  | 2016-08-26 | 2016-08-26 |  | 160005291625 |  |  | 160005071625 |  |  | 160003941625 | [11 empty] | 162001851625 |  |  | 155002351624 |  | 2016-09-03 | 2016-09-03 | X
48 | 1000000086 | ΥMI 1563 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-14 | 2016-07-14 |  |  | 2016-08-30 | 2016-08-30 |  | 160001771625 |  |  | 160003841625 |  |  | 160001811625 | [11 empty] | 162001331625 |  |  | 155002011624 |  | 2016-09-03 | 2016-09-03 | X
49 | 1000000608 | ZKZ 9715 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-14 | 2016-07-14 |  |  | 2016-09-13 | 2016-09-13 |  | 160004421625 |  |  | 160004581625 |  |  | 160005521625 | [11 empty] | 162006341632 |  |  | 155004831630 |  |  |  | O
50 | 1000000599 | ZKZ 9706 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-14 | 2016-07-14 |  |  | 2016-09-12 | 2016-09-12 |  | 160002631625 |  |  | 160004071625 |  |  | 160005331625 | [11 empty] | 162000201625 |  |  | 155002801625 |  |  |  | O
51 | 1000000614 | ΖΚΖ 9721 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-15 | 2016-07-15 |  |  | 2016-09-14 | 2016-09-14 |  | 160004121625 |  |  | 160000391625 |  |  | 160003111625 | [11 empty] | 162003691630 |  |  | 155003001630 |  |  |  | O
52 | 1000000612 | ΖΚΖ 9719 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-15 | 2016-07-15 |  |  | 2016-09-13 | 2016-09-13 |  | 160001591625 |  |  | 160005541625 |  |  | 160003151625 | [11 empty] | 162001981625 |  |  | 155003411630 |  |  |  | O
53 | 1000000613 | ΖΚΖ 9720 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-15 | 2016-07-15 |  |  | 2016-09-13 | 2016-09-13 |  | 160005441625 |  |  | 160006141630 |  |  | 160000381625 | [11 empty] | 162001421625 |  |  | 155003431630 |  |  |  | O
54 | 1000000081 | ΥΜΙ 1557 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-15 | 2016-07-15 |  |  | 2016-09-02 | 2016-09-02 |  | 160001001625 |  |  | 160006061626 |  |  | 160006001625 | [11 empty] | 162005101632 |  |  | 155002661625 |  | 2016-09-10 | 2016-09-10 | X
55 | 1000000076 | ΥΜΙ 1551 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-15 | 2016-07-15 |  |  | 2016-08-25 | 2016-08-25 |  | 160001931625 |  |  | 160003581625 |  |  | 160004381625 | [11 empty] | 162001001625 |  |  | 155000971624 |  | 2016-09-10 | 2016-09-10 | X
56 | 1000000074 | ΥΜΙ 1548 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-15 | 2016-07-15 |  |  | 2016-08-27 | 2016-08-27 |  | 160003521625 |  |  | 160000591625 |  |  | 160005341625 | [11 empty] | 162001951625 |  |  | 155001331624 |  | 2016-09-10 | 2016-09-10 | X
57 | 1000000190 | ΥΝΝ 9712 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-15 | 2016-07-15 |  |  | 2016-08-29 | 2016-08-29 |  | 160004001625 |  |  | 160004431625 | [14 empty] | 162001761625 |  |  | 155001611624 |  | 2016-09-10 | 2016-09-10 | X
58 | 1000000191 | ΥΝΝ 9714 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-15 | 2016-07-15 |  |  | 2016-08-29 | 2016-08-29 |  | 160003261625 |  |  | 160005871625 | [14 empty] | 162001491625 |  |  | 155002421624 |  | 2016-09-10 | 2016-09-10 | X
59 | 1000000192 | ΥΝΝ 9716 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-15 | 2016-07-15 |  |  | 2016-09-03 | 2016-09-03 |  | 160010351630 |  |  | 160011081630 | [14 empty] | 162001161625 |  |  | 155000991624 |  | 2016-09-10 | 2016-09-10 | X
60 | 1000000193 | ΥΝΝ 9717 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-15 | 2016-07-15 |  |  | 2016-08-29 | 2016-08-29 |  | 160001411625 |  |  | 160003861625 | [14 empty] | 162000401625 |  |  | 155000941624 |  | 2016-09-10 | 2016-09-10 | X
61 | 1000000196 | ΥΝΝ 9720 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-15 | 2016-07-15 |  |  | 2016-08-30 | 2016-08-30 |  | 160001601625 |  |  | 160005861625 | [14 empty] | 162000071625 |  |  | 155000811624 |  | 2016-09-10 | 2016-09-10 | X
62 | 1000000198 | ΥΝΝ 9722 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-15 | 2016-07-15 |  |  | 2016-08-30 | 2016-08-30 |  | 160001431625 |  |  | 160001131625 | [14 empty] | 162001061625 |  |  | 155001551624 |  | 2016-09-03 | 2016-09-03 | X
63 | 1000000624 | ΖΚΖ 9732 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-16 | 2016-07-16 |  |  | 2016-09-15 | 2016-09-15 |  | 160009431630 |  |  | 160010661630 |  |  | 160008081630 | [11 empty] | 162003681630 |  |  | 155004081630 |  |  |  | O
64 | 1000000618 | ΖΚΖ 9726 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-16 | 2016-07-16 |  |  | 2016-09-14 | 2016-09-14 |  | 160004551625 |  |  | 160002211625 |  |  | 160004171625 | [11 empty] | 162002011625 |  |  | 155003441630 |  |  |  | O
65 | 1000000203 | ΥΝΝ 9727 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-16 | 2016-07-16 |  |  | 2016-08-30 | 2016-08-30 |  | 160002551625 |  |  | 160003901625 | [14 empty] | 162000081625 |  |  | 155002831626 |  |  |  | X
66 | 1000000080 | ΥΜΙ 1566 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-16 | 2016-07-16 |  |  | 2016-08-31 | 2016-08-31 |  | 160021111633 |  |  | 160012671632 |  |  | 160019361633 | [11 empty] | 162002031625 |  |  | 155001451624 |  |  |  | X
67 | 1000000090 | ΥΜΙ 1567 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-16 | 2016-07-16 |  |  | 2016-08-31 | 2016-08-31 |  | 160005621625 |  |  | 160002351625 |  |  | 160019361633 | [11 empty] | 162001451625 |  |  | 155001801624 |  |  |  | X
68 | 1000000083 | ΥΜΙ 1560 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-16 | 2016-07-16 |  |  | 2016-08-29 | 2016-08-29 |  | 160005111625 |  |  | 160001691625 |  |  | 160002951625 | [11 empty] | 162001321625 |  |  | 155000661624 |  | 2016-09-10 | 2016-09-10 | X
69 | 1000000091 | ΥΜΙ 1569 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-16 | 2016-07-16 |  |  | 2016-09-01 | 2016-09-01 |  | 160019711633 |  |  | 160012841632 |  |  | 160020901633 | [11 empty] | 162000271625 |  |  | 155002151624 |  |  |  | X
70 | 1000000002 | ΥΕΚ 5248 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-16 | 2016-07-16 |  |  | 2016-08-23 | 2016-08-23 |  | 160005061625 |  |  | 160005811625 |  |  | 160003731625 | [11 empty] | 162001741625 |  |  | 155001571624 |  | 2016-08-27 | 2016-08-27 | X
71 | 1000000094 | ΥΜΙ 1576 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-18 | 2016-07-18 |  |  | 2016-08-31 | 2016-08-31 |  | 160014091632 |  |  | 160002601625 |  |  | 160003641625 | [11 empty] | 162001721625 |  |  | 155001191624 |  |  |  | X
72 | 1000000093 | ΥΜΙ 1575 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-18 | 2016-07-18 |  |  | 2016-09-03 | 2016-09-03 |  | 160020591633 |  |  | 160017651633 |  |  | 160021231633 | [11 empty] | 162005181632 |  |  | 155001531624 |  |  |  | X
73 | 1000000098 | ΥΜΙ 1583 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-18 | 2016-07-18 |  |  | 2016-09-02 | 2016-09-02 |  | 160000941625 |  |  | 160001861625 |  |  | 160005211625 | [11 empty] | 162006521632 |  |  | 155000961624 |  |  |  | X
74 | 1000000206 | ΥΝΝ 9730 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-18 | 2016-07-18 |  |  | 2016-08-31 | 2016-08-31 |  | 160003921625 |  |  | 160001291625 | [14 empty] | 162001881625 |  |  | 155001731624 |  |  |  | X
75 | 1000000205 | ΥΝΝ 9729 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-18 | 2016-07-18 |  |  | 2016-08-30 | 2016-08-30 |  | 160001341625 |  |  | 160005301625 | [14 empty] | 162001601625 |  |  | 155000531624 |  |  |  | X
76 | 1000000201 | ΥΝΝ 9725 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-18 | 2016-07-18 |  |  | 2016-08-30 | 2016-08-30 |  | 160003071625 |  |  | 160003741625 | [14 empty] | 162001301625 |  |  | 155001541624 |  |  |  | X
77 | 1000000194 | ΥΝΝ 9718 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-18 | 2016-07-18 |  |  | 2016-08-30 | 2016-08-30 |  | 160005191625 |  |  | 160002541625 | [14 empty] | 162001211625 |  |  | 155001311624 |  | 2016-09-10 | 2016-09-10 | X
78 | 1000000179 | ΥΝΝ 9701 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-18 | 2016-07-18 |  |  | 2016-08-25 | 2016-08-25 |  | 160004111625 |  |  | 160004591625 | [14 empty] | 162001891625 |  |  | 155001021624 |  | 2016-09-03 | 2016-09-03 | X
79 | 1000000597 | ΖΚΖ 9704 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-18 | 2016-07-18 |  |  | 2016-09-12 | 2016-09-12 |  | 160002181625 |  |  | 160003881625 |  |  | 160004081625 | [11 empty] | 162001381625 |  |  | 155003281630 |  |  |  | O
80 | 1000000603 | ΖΚΖ 9710 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-18 | 2016-07-18 |  |  | 2016-09-12 | 2016-09-12 |  | 160009441630 |  |  | 160001921625 |  |  | 160002761625 | [11 empty] | 162000881625 |  |  | 155004391630 |  |  |  | O
81 | 1000000616 | ΖΚΖ 9723 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-18 | 2016-07-18 |  |  | 2016-09-14 | 2016-09-14 |  | 160002511625 |  |  | 160005131625 |  |  | 160004661625 | [11 empty] | 162002881630 |  |  | 155005061631 |  |  |  | O
82 | 1000000210 | ΥΝΝ 9734 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-19 | 2016-07-19 |  |  | 2016-08-31 | 2016-08-31 |  | 160019471633 |  |  | 160018741633 | [14 empty] | 162001971625 |  |  | 155002631625 |  | 2016-09-03 | 2016-09-03 | X
83 | 1000000209 | ΥΝΝ 9733 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-19 | 2016-07-19 |  |  | 2016-08-31 | 2016-08-31 |  | 16000351625 |  |  | 160002771625 | [14 empty] | 162000241625 |  |  | 155002091624 |  |  |  | X
84 | 1000000207 | ΥΝΝ 9731 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-19 | 2016-07-19 |  |  | 2016-08-31 | 2016-08-31 |  | 160000811625 |  |  | 160004901625 | [14 empty] | 162000961625 |  |  | 155002751625 |  |  |  | X
85 | 1000000211 | ΥΝΝ 9735 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-19 | 2016-07-19 |  |  | 2016-08-31 | 2016-08-31 |  | 160005161625 |  |  | 160016521632 | [14 empty] | 162000511625 |  |  | 155001801624 |  |  |  | X
86 | 1000000212 | ΥΝΝ 9736 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-19 | 2016-07-19 |  |  | 2016-09-01 | 2016-09-01 |  | 160002461625 |  |  | 160002481625 | [14 empty] | 162000051625 |  |  | 155001051624 |  |  |  | X
87 | 1000000172 | ΥΝΝ 9693 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-19 | 2016-07-19 |  |  | 2016-08-26 | 2016-08-26 |  | 160004821625 |  |  | 160001251625 | [14 empty] | 162000851625 |  |  | 155002381624 |  | 2016-09-03 | 2016-09-03 | X
88 | X | ΥΜΙ 1582 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-19 | 2016-07-19 |  |  | 2016-09-09 | 2016-09-09 |  | 160001161625 |  |  | 160001641625 |  |  | 160006011625 | [11 empty] | 162002751630 |  |  | 155003591630 |  |  |  | X
89 | 1000000103 | ΥΜΙ 1591 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-19 | 2016-07-19 |  |  | 2016-08-22 | 2016-08-22 |  | 160001831625 |  |  | 160003801625 |  |  | 160001231625 | [11 empty] | 162000011625 |  |  | 155001241624 |  |  |  | X
90 | 1000000104 | ΥΜΙ 1592 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-19 | 2016-07-19 |  |  | 2016-09-01 | 2016-09-01 |  | 160012171632 |  |  | 160015801632 |  |  | 160019931633 | [11 empty] | 162004681632 |  |  | 155000791624 |  |  |  | X
91 | 1000000101 | ΥΜΙ 1588 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-19 | 2016-07-19 |  |  | 2016-09-06 | 2016-09-06 |  | 160002431625 |  |  | 160001581625 |  |  | 160002131625 | [11 empty] | 162003081630 |  |  | 155001391624 |  |  |  | X
92 | 1000000105 | ΥΜΙ 1593 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-19 | 2016-07-19 |  |  | 2016-08-22 | 2016-08-22 |  | 160001261625 |  |  | 160003821625 |  |  | 160004521625 | [11 empty] | 162002061625 |  |  | 155001781624 |  |  |  | X
93 | 1000000100 | ΥΜΙ 1587 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-19 | 2016-07-19 |  |  | 2016-09-01 | 2016-09-01 |  | 160015731632 |  |  | 160019351633 |  |  | 160013601632 | [11 empty] | 162000811625 |  |  | 15500711624 |  |  |  | X
94 | 1000000626 | ΖΚΖ 9734 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-19 | 2016-07-19 |  |  | 2016-09-15 | 2016-09-15 |  | 160009271630 |  |  | 160010241630 |  |  | 160007401630 | [11 empty] | 162004051630 |  |  | 155003301630 |  |  |  | O
95 | 1000000610 | ΖΚΖ 9717 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-19 | 2016-07-19 |  |  | 2016-09-13 | 2016-09-13 |  | 160005661625 |  |  | 160001801625 |  |  | 160002171625 | [11 empty] | 162000991625 |  |  | 155003361630 |  |  |  | O
96 | 1000000595 | ΖΚΖ 9702 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-19 | 2016-07-19 |  |  | 2016-09-14 | 2016-09-14 |  | 160003011625 |  |  | 160004491625 |  |  | 160003871625 | [11 empty] | 162003621630 |  |  | 155003851630 |  |  |  | O
97 | 1000000627 | ΖΚΖ 9735 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-20 | 2016-07-20 |  |  | 2016-09-15 | 2016-09-15 |  | 160009691630 |  |  | 160007941630 |  |  | 160010121630 | [11 empty] | 162002571630 |  |  | 155003621630 |  |  |  | O
98 |  | ΖΚΖ 9737 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-20 | 2016-07-20 | [30 empty] | X
99 |  | ΖΚΖ 9888 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-20 | 2016-07-20 | [30 empty] | X
100 |  | ΖΚΖ 9963 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-20 | 2016-07-20 | [30 empty] | X
101 | 1000000630 | ΖΚΖ 9738 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-20 | 2016-07-20 |  |  | 2016-09-15 | 2016-09-15 |  | 160007231630 |  |  | 160010281630 |  |  | 160009011630 | [11 empty] | 162004181630 |  |  | 155007721632 |  |  |  | O
102 | 1000000107 | ΥΜΙ 1595 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-20 | 2016-07-20 |  |  | 2016-09-02 | 2016-09-02 |  | 160004961625 |  |  | 160002841625 |  |  | 160004981625 | [11 empty] | 162004691632 |  |  | 155001141624 |  |  |  | X
103 | 1000000092 | ΥΜΙ 1570 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-20 | 2016-07-20 |  |  | 2016-09-01 | 2016-09-01 |  | 160000751625 |  |  | 160020201633 |  |  | 160020881633 | [11 empty] | 162001011625 |  |  | 155002441624 |  |  |  | X
104 | 1000000102 | ΥΜΙ 1590 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-20 | 2016-07-20 |  |  | 2016-09-01 | 2016-09-01 |  | 160005651625 |  |  | 160000731625 |  |  | 160002311625 | [11 empty] | 162001251625 |  |  | 155001521624 |  |  |  | X
105 | 1000000119 | ΥΜΙ 1613 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-20 | 2016-07-20 |  |  | 2016-09-08 | 2016-09-08 |  | 160007181630 |  |  | 160020361633 |  |  | 160003351625 | [11 empty] | 162001091625 |  |  | 155002051624 |  |  |  | X
106 | 1000000106 | ΥΜΙ 1594 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-20 | 2016-07-20 |  |  | 2016-09-02 | 2016-09-02 |  | 160003771625 |  |  | 160002071625 |  |  | 160002321625 | [11 empty] | 162005961632 |  |  | 155002401624 |  |  |  | X
107 | 1000000214 | ΥΝΝ 9738 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-20 | 2016-07-20 |  |  | 2016-09-01 | 2016-09-01 |  | 160020191633 |  |  | 160002901625 | [14 empty] | 162000031625 |  |  | 155001231624 |  |  |  | X
108 | 1000000216 | ΥΝΝ 9740 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-20 | 2016-07-20 |  |  | 2016-09-01 | 2016-09-01 |  | 160012801632 |  |  | 160019871633 | [14 empty] | 162000321625 |  |  | 155001401624 |  | 2016-09-03 | 2016-09-03 | X
109 | 1000000220 | ΥΝΝ 9744 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-20 | 2016-07-20 |  |  | 2016-09-01 | 2016-09-01 |  | 160002611625 |  |  | 160004321625 | [14 empty] | 162000111625 |  |  | 155001371624 |  | 2016-09-03 | 2016-09-03 | X
110 | 1000000014 | ΥΕΚ 5263 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-20 | 2016-07-20 |  |  | 2016-08-25 | 2016-08-25 |  | 160005151625 |  |  | 160003061625 |  |  | 160002491625 | [11 empty] | 162000281625 |  |  | 155002621625 |  | 2016-09-03 | 2016-09-03 | X
111 | 1000000226 | ΥΝΝ 9750 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-21 | 2016-07-21 |  |  | 2016-09-02 | 2016-09-02 |  | 160002521625 |  |  | 160002961625 | [14 empty] | 162006401632 |  |  | 155001261624 |  |  |  | X
112 | 1000000227 | ΥΝΝ 9752 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-21 | 2016-07-21 |  |  | 2016-09-06 | 2016-09-06 |  | 160001501625 |  |  | 160000331625 | [14 empty] | 162003541630 |  |  | 155001761624 |  |  |  | X
113 | 1000000225 | ΥΝΝ 9749 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-21 | 2016-07-21 |  |  | 2016-09-02 | 2016-09-02 |  | 160002421625 |  |  | 160003691625 | [14 empty] | 162004791632 |  |  | 155001011624 |  |  |  | X
114 | 1000000222 | ΥΝΝ 9746 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-21 | 2016-07-21 |  |  | 2016-09-01 | 2016-09-01 |  | 160005581625 |  |  | 160003051625 | [14 empty] | 162000631625 |  |  | 155001071624 |  |  |  | X
115 | 1000000224 | ΥΝΝ 9748 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-21 | 2016-07-21 |  |  | 2016-09-02 | 2016-09-02 |  | 160004141625 |  |  | 160001841625 | [14 empty] | 162004701632 |  |  | 155001891624 |  |  |  | X
116 | 1000000248 | ΥΝΝ 9773 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-21 | 2016-07-21 |  |  | 2016-09-05 | 2016-09-05 |  | 160004671625 |  |  | 160003231625 | [14 empty] | 162004301630 |  |  | 155001271624 |  | 2016-09-10 | 2016-09-10 | X
117 | 1000000219 | ΥΝΝ 9743 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-21 | 2016-07-21 |  |  | 2016-09-03 | 2016-09-03 |  | 160020861633 |  |  | 160001021625 | [14 empty] | 162006011632 |  |  | 155000771624 |  |  |  | X
118 | 1000000082 | ΥΜΙ 1559 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-21 | 2016-07-21 |  |  | 2016-08-26 | 2016-08-26 |  | 160000341625 |  |  | 160003551625 |  |  | 160005381625 | [11 empty] | 162001811625 |  |  | 155001601624 |  | 2016-09-10 | 2016-09-10 | X
119 | 1000000084 | ΥΜΙ 1561 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-21 | 2016-07-21 |  |  | 2016-08-29 | 2016-08-29 |  | 160003811625 |  |  | 160004571625 |  |  | 160004101625 | [11 empty] | 162001271625 |  |  | 155002191624 |  |  |  | X
120 | 1000000077 | ΥΜΙ 1552 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-21 | 2016-07-21 |  |  | 2016-08-30 | 2016-08-30 |  | 160001441625 |  |  | 160005081625 |  |  | 160005851625 | [11 empty] | 162000221625 |  |  | 155000761624 |  | 2016-09-10 | 2016-09-10 | X
121 | 1000000087 | ΥΜΙ 1564 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-21 | 2016-07-21 |  |  | 2016-08-31 | 2016-08-31 |  | 160001941625 |  |  | 160003471625 |  |  | 160002411625 | [11 empty] | 162000381625 |  |  | 155002111624 |  | 2016-09-03 | 2016-09-03 | X
122 | 1000000088 | ΥΜΙ 1565 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-21 | 2016-07-21 |  |  | 2016-08-30 | 2016-08-30 |  | 160003201625 |  |  | 160005751625 |  |  | 160001211625 | [11 empty] | 162001541625 |  |  | 155002651625 |  |  |  | X
123 | 1000000085 | ΥΜΙ 1562 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-21 | 2016-07-21 |  |  | 2016-08-30 | 2016-08-30 |  | 160005321625 |  |  | 160000711625 |  |  | 160004261625 | [11 empty] | 162001961625 |  |  | 155000521624 |  |  |  | X
124 | 1000000637 | ΖΚΖ 9745 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-21 | 2016-07-21 |  |  | 2016-09-16 | 2016-09-16 |  | 160008091630 |  |  | 160006451630 |  |  | 160010441630 | [11 empty] | 162002951630 |  |  | 155003291630 |  |  |  | O
125 | 1000000639 | ΖΚΖ 9747 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-21 | 2016-07-21 |  |  | 2016-09-16 | 2016-09-16 |  | 160009971630 |  |  | 160009421630 |  |  | 160012061630 | [11 empty] | 162003481630 |  |  | 155003821630 |  |  |  | O
126 | 1000000029 | ΥΕΚ 5281 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-22 | 2016-07-22 |  |  | 2016-09-06 | 2016-09-06 |  | 160020451633 |  |  | 160021071633 |  |  | 160016241632 | [11 empty] | 162003671630 |  |  | 155002671625 |  |  |  | X
127 | 1000000011 | ΥΕΚ 5259 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-22 | 2016-07-22 |  |  | 2016-08-24 | 2016-08-24 |  | 160001701625 |  |  | 160003141625 |  |  | 160003331625 | [11 empty] | 162000821625 |  |  | 155001131624 |  | 2016-09-10 | 2016-09-10 | X
128 | 1000000075 | ΥΜΙ 1550 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-22 | 2016-07-22 |  |  | 2016-08-25 | 2016-08-25 |  | 160004971625 |  |  | 160004251625 |  |  | 160005671625 | [11 empty] | 162000761625 |  |  | 155000611624 |  |  |  | X
129 | 1000000099 | ΥΜΙ 1586 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-22 | 2016-07-22 |  |  | 2016-09-01 | 2016-09-01 |  | 160001711625 |  |  | 160004621625 |  |  | 160000641625 | [11 empty] | 162000151625 |  |  | 155002061624 |  |  |  | X
130 | 1000000095 | ΥΜΙ 1578 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-22 | 2016-07-22 |  |  | 2016-09-01 | 2016-09-01 |  | 160015061632 |  |  | 160020981633 | [14 empty] | 162001831625 |  |  | 155000551624 |  |  |  | X
131 | 1000000110 | ΥΜΙ 1598 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-22 | 2016-07-22 |  |  | 2016-09-02 | 2016-09-02 |  | 160001911625 |  |  | 160004651625 |  |  | 160002291625 | [11 empty] | 162006071632 |  |  | 155002731625 |  |  |  | X
132 | 1000000233 | ΥΝΝ 9758 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-22 | 2016-07-22 |  |  | 2016-09-02 | 2016-09-02 |  | 160005641625 |  |  | 160005531625 | [14 empty] | 162005621632 |  |  | 155001321624 |  |  |  | X
133 | 1000000234 | ΥΝΝ 9759 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-22 | 2016-07-22 |  |  | 2016-09-02 | 2016-09-02 |  | 160003371625 |  |  | 160005461625 | [14 empty] | 162004561632 |  |  | 155000641624 |  |  |  | X
134 | 1000000237 | ΥΝΝ 9762 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-22 | 2016-07-22 |  |  | 2016-09-09 | 2016-09-09 |  | 160003271625 |  |  | 160002861625 | [14 empty] | 162003721630 |  |  | 155003211630 |  |  |  | X
135 | 1000000232 | ΥΝΝ 9757 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-22 | 2016-07-22 |  |  | 2016-09-02 | 2016-09-02 |  | 160002991625 |  |  | 160000261625 | [14 empty] | 162006511632 |  |  | 155002821626 |  |  |  | X
136 | 1000000231 | ΥΝΝ 9756 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-22 | 2016-07-22 |  |  | 2016-09-02 | 2016-09-02 |  | 160001901625 |  |  | 160002231625 | [14 empty] | 162005441632 |  |  | 155001821624 |  | 2016-09-03 | 2016-09-03 | X
137 | 1000000229 | ΥΝΝ 9754 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-22 | 2016-07-22 |  |  | 2016-09-03 | 2016-09-03 |  | 160019091633 |  |  | 160007341630 | [14 empty] | 162005571632 |  |  | 155001711624 |  |  |  | O
138 | 1000000643 | ΖΚΖ 9751 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-22 | 2016-07-22 |  |  | 2016-09-17 | 2016-09-17 |  | 160009831630 |  |  | 160008851630 |  |  | 160011241630 | [11 empty] | 162003281630 |  |  | 155003791630 |  |  |  | O
139 |  | ΖΚΖ 9752 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-22 | 2016-07-22 | [30 empty] | X
140 |  | ΖΚΖ 9753 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-22 | 2016-07-22 | [30 empty] | X
141 | 1000000650 | ΖΚΖ 9758 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-22 | 2016-07-22 |  |  | 2016-09-20 | 2016-09-20 |  | 160007741630 |  |  | 160010081630 |  |  | 160007511630 | [11 empty] | 162003901630 |  |  | 155005331631 |  |  |  | O
142 |  | ΖΚΖ 9743 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-23 | 2016-07-23 | [30 empty] | X
143 | 1000000656 | ΖΚΖ 9764 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-23 | 2016-07-23 |  |  | 2016-09-19 | 2016-09-19 |  | 160006701630 |  |  | 16001081630 |  |  | 160011281630 | [11 empty] | 162001431625 |  |  | 155003561630 |  |  |  | O
144 | 1000000653 | ΖΚΖ 9761 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-23 | 2016-07-23 |  |  | 2016-09-17 | 2016-09-17 |  | 160009611630 |  |  | 160010051630 |  |  | 160009561630 | [11 empty] | 162003701630 |  |  | 155004951630 |  |  |  | O
145 | 1000000138 | ΥΜΙ 1642 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-23 | 2016-07-23 |  |  | 2016-08-22 | 2016-08-22 |  | 160004271625 |  |  | 160003661625 |  |  | 160005041625 | [11 empty] | 162002131625 |  |  | 155001631624 |  | 2016-09-03 | 2016-09-03 | X
146 | 1000000117 | ΥΜΙ 1611 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-23 | 2016-07-23 |  |  | 2016-09-06 | 2016-09-06 |  | 160014531632 |  |  | 160017331633 |  |  | 160012331632 | [11 empty] | 162004061630 |  |  | 155000541624 |  |  |  | X
147 | 1000000240 | ΥΝΝ 9765 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-23 | 2016-07-23 |  |  | 2016-09-06 | 2016-09-06 |  | 160004891625 |  |  | 160002301625 | [14 empty] | 162005331632 |  |  | 155000801624 |  |  |  | X
148 | 1000000286 | ΥΝΝ 9815 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-23 | 2016-07-23 |  |  | 2016-09-09 | 2016-09-09 |  | 160019151633 |  |  | 160019641633 | [14 empty] | 162003121630 |  |  | 155003241630 |  |  |  | X
149 | 1000000262 | ΥΝΝ 9788 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-23 | 2016-07-23 |  |  | 2016-09-09 | 2016-09-09 |  | 160013011632 |  |  | 160004701625 | [14 empty] | 162001311625 |  |  | 155004121630 |  |  |  | X
150 | 1000000221 | ΥΝΝ 9745 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-23 | 2016-07-23 |  |  | 2016-09-01 | 2016-09-01 |  | 160002751625 |  |  | 160004511625 | [14 empty] | 162001231625 |  |  | 155001811624 |  |  |  | X
151 | 1000000244 | ΥΝΝ 9769 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-23 | 2016-07-23 |  |  | 2016-09-06 | 2016-09-06 |  | 160019741633 |  |  | 160019991633 | [14 empty] | 162005841632 |  |  | 155000751624 |  |  |  | X
152 | 1000000218 | ΥΝΝ 9742 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-23 | 2016-07-23 |  |  | 2016-09-05 | 2016-09-05 |  | 160003041625 |  |  | 160001661625 | [14 empty] | 162005731632 |  |  | 155002001624 |  |  |  | X
153 | 1000000241 | ΥΝΝ 9766 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-25 | 2016-07-25 |  |  | 2016-09-03 | 2016-09-03 |  | 160002661625 |  |  | 160005971625 | [14 empty] | 162001511625 |  |  | 155002781625 |  |  |  | X
154 | 1000000242 | ΥΝΝ 9767 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-25 | 2016-07-25 |  |  | 2016-09-06 | 2016-09-06 |  | 160011661630 |  |  | 160012241632 | [14 empty] | 162004111630 |  |  | 155001651624 |  |  |  | X
155 | 1000000245 | ΥΝΝ 9770 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-25 | 2016-07-25 |  |  | 2016-09-05 | 2016-09-05 |  | 160004481625 |  |  | 160000551625 | [14 empty] | 162006551632 |  |  | 155001181624 |  |  |  | X
156 | 1000000239 | ΥΝΝ 9764 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-25 | 2016-07-25 |  |  | 2016-09-03 | 2016-09-03 |  | 160008941630 |  |  | 160009681630 | [14 empty] | 162002701630 |  |  | 155001201624 |  |  |  | X
157 | 1000000116 | ΥΜΙ 1606 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-25 | 2016-07-25 |  |  | 2016-09-06 | 2016-09-06 |  | 160017531633 |  |  | 160013261632 |  |  | 160011431630 | [11 empty] | 162004111630 |  |  | 155002481624 |  |  |  | X
158 | 1000000114 | ΥΜΙ 1603 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-25 | 2016-07-25 |  |  | 2016-08-31 | 2016-08-31 |  | 160020631633 |  |  | 160015921632 |  |  | 160020021633 | [11 empty] | 162001641625 |  |  | 155002251624 |  |  |  | X
159 | 1000000115 | ΥΜΙ 1604 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-25 | 2016-07-25 |  |  | 2016-09-03 | 2016-09-03 |  | 160020071633 |  |  | 160018551633 |  |  | 160009621630 | [11 empty] | 162002111625 |  |  | 155002851626 |  |  |  | X
160 | 1000000113 | ΥΜΙ 1602 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-25 | 2016-07-25 |  |  | 2016-09-03 | 2016-09-03 |  | 160009021630 |  |  | 160011121630 |  |  | 160021051633 | [11 empty] | 162006021632 |  |  | 155001851624 |  |  |  | X
161 | 1000000111 | ΥΜΙ 1599 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-25 | 2016-07-25 |  |  | 2016-09-07 | 2016-09-07 |  | 160000951625 |  |  | 160012521632 |  |  | 160020761633 | [11 empty] | 162004991632 |  |  | 155000921624 |  |  |  | X
162 | 1000000096 | ΥΜΙ 1579 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-25 | 2016-07-25 |  |  | 2016-09-01 | 2016-09-01 |  | 160015631632 |  |  | 160016481632 |  |  | 160013521632 | [11 empty] | 162001341625 |  |  | 155001561624 |  |  |  | X
163 |  | ΖΚΖ 9845 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-25 | 2016-07-25 | [30 empty] | X
164 | 1000000660 | ΖΚΖ 9768 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-25 | 2016-07-25 |  |  | 2016-09-19 | 2016-09-19 |  | 160012701632 |  |  | 160008831630 |  |  | 160015961632 | [11 empty] | 162004071630 |  |  | 155007961632 |  |  |  | O
165 |  | ΖΚΖ 9767 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-25 | 2016-07-25 | [30 empty] | X
166 | 1000000657 | ΖΚΖ 9765 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-25 | 2016-07-25 |  |  | 2016-09-20 | 2016-09-20 |  | 160009061630 |  |  | 160010001630 |  |  | 160007781630 | [11 empty] | 162002341630 |  |  | 155005281631 |  |  |  | O
167 |  | ΖΚΖ 9776 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-25 | 2016-07-25 | [30 empty] | X
168 |  | ΖΚΖ 9965 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 | [30 empty] | X
169 | 1000000621 | ΖΚΖ 9729 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 |  |  | 2016-09-19 | 2016-09-19 |  | 160006651630 |  |  | 160007171630 |  |  | 160008331630 | [11 empty] | 162003371630 |  |  | 155003521630 |  |  |  | O
170 |  | ΖΚΖ 9836 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 | [30 empty] | X
171 | 1000000620 | ΖΚΖ 9728 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 |  |  | 2016-09-15 | 2016-09-15 |  | 160011991630 |  |  | 160010731630 |  |  | 160009661630 | [11 empty] | 162003141630 |  |  | 155005051631 |  |  |  | O
172 |  | ΖΚΖ 9908 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 | [30 empty] | X
173 | 1000000109 | ΥΜΙ 1597 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 |  |  | 2016-09-02 | 2016-09-02 |  | 160003401625 |  |  | 160004091625 |  |  | 160004031625 | [11 empty] | 162006371632 |  |  | 155002031624 |  |  |  | X
174 | 1000000108 | ΥΜΙ 1596 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 |  |  | 2016-09-02 | 2016-09-02 |  | 160002381625 |  |  | 160002981625 |  |  | 160003101625 | [11 empty] | 162005071632 |  |  | 155002411624 |  |  |  | X
175 | 1000000118 | ΥΜΙ 1612 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 |  |  | 2016-09-10 | 2016-09-10 |  | 160017371633 |  |  | 160020371633 |  |  | 160000971625 | [11 empty] | 162001861625 |  |  | 155003911630 |  |  |  | O
176 | 1000000121 | ΥΜΙ 1615 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 |  |  | 2016-09-08 | 2016-09-08 |  | 160006601630 |  |  | 160019171633 |  |  | 160004221625 | [11 empty] | 162005891632 |  |  | 155000681624 |  |  |  | X
177 | 1000000122 | ΥΜΙ 1618 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 |  |  | 2016-09-05 | 2016-09-05 |  | 160006041626 |  |  | 160001111625 |  |  | 160001331625 | [11 empty] | 162003041630 |  |  | 155000851624 |  |  |  | X
178 | 1000000120 | ΥΜΙ 1614 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 |  |  | 2016-09-10 | 2016-09-10 |  | 160020771633 |  |  | 160020741633 |  |  | 160003781625 | [11 empty] | 162006411632 |  |  | 155003261630 |  |  |  | O
179 | 1000000200 | ΥΝΝ 9724 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 |  |  | 2016-08-31 | 2016-08-31 |  | 160003081625 |  |  | 160001741625 | [14 empty] | 162000341625 |  |  | 155001161624 |  | 2016-09-10 | 2016-09-10 | X
180 | 1000000215 | ΥΝΝ 9739 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 |  |  | 2016-09-01 | 2016-09-01 |  | 160012201632 |  |  | 160015571632 | [14 empty] | 162005391632 |  |  | 155000511624 |  |  |  | X
181 | 1000000213 | ΥΝΝ 9737 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 |  |  | 2016-09-01 | 2016-09-01 |  | 160000871625 |  |  | 160015741632 | [14 empty] | 162001781625 |  |  | 155001061624 |  |  |  | X
182 | 1000000249 | ΥΝΝ 9774 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 |  |  | 2016-09-10 | 2016-09-10 |  | 160019821633 |  |  | 160019631633 | [14 empty] | 162001161625 |  |  | 155003421630 |  |  |  | O
183 | 1000000246 | ΥΝΝ 9771 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 |  |  | 2016-09-05 | 2016-09-05 |  | 160001731625 |  |  | 160001061625 | [14 empty] | 162003221630 |  |  | 155001681624 |  | 2016-09-10 | 2016-09-10 | X
184 | 1000000247 | ΥΝΝ 9772 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-26 | 2016-07-26 |  |  | 2016-09-05 | 2016-09-05 |  | 160005121625 |  |  | 160001301625 | [14 empty] | 162005211632 |  |  | 155001871624 |  |  |  | X
185 | 1000000253 | ΥΝΝ 9779 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 |  |  | 2016-09-05 | 2016-09-05 |  | 160005401625 |  |  | 160002621625 | [14 empty] | 162004191630 |  |  | 155001421624 |  |  |  | X
186 | 1000000251 | ΥΝΝ 9776 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 |  |  | 2016-09-05 | 2016-09-05 |  | 160004021625 |  |  | 160006031626 | [14 empty] | 162005471632 |  |  | 155001941624 |  |  |  | X
187 | 1000000254 | ΥΝΝ 9780 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 |  |  | 2016-09-07 | 2016-09-07 |  | 160014701632 |  |  | 160020211632 | [14 empty] | 162004101630 |  |  | 155002161624 |  |  |  | X
188 | 1000000255 | ΥΝΝ 9781 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 |  |  | 2016-08-30 | 2016-08-30 |  | 160005711625 |  |  | 160005411625 | [14 empty] | 162000391625 |  |  | 155001091624 |  |  |  | X
189 | 1000000256 | ΥΝΝ 9782 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 |  |  | 2016-09-07 | 2016-09-07 |  | 160020791633 |  |  | 160005271625 | [14 empty] | 162004731632 |  |  | 155001441624 |  |  |  | X
190 | 1000000252 | ΥΝΝ 9778 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 |  |  | 2016-09-10 | 2016-09-10 |  | 160005511625 |  |  | 160019491633 | [14 empty] | 162001561625 |  |  | 155004111630 |  |  |  | O
191 | 1000000126 | ΥΜΙ 1625 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 |  |  | 2016-08-29 | 2016-08-29 |  | 160003291625 |  |  | 160004691625 |  |  | 160005471625 | [11 empty] | 162002081625 |  |  | 155001151624 |  |  |  | X
192 | X | ΥΜΙ 1626 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 |  |  | 2016-09-09 | 2016-09-09 |  | 160000451625 |  |  | 160016791632 |  |  | 160002441625 | [11 empty] | 162002411630 |  |  | 155004241630 |  |  |  | X
193 | 1000000127 | ΥΜΙ 1627 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 |  |  | 2016-09-07 | 2016-09-07 |  | 160010921630 |  |  | 160008131630 |  |  | 160013421632 | [11 empty] | 162002681630 |  |  | 155000861624 |  |  |  | X
194 | 1000000125 | ΥΜΙ 1622 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 |  |  | 2016-09-05 | 2016-09-05 |  | 160001011625 |  |  | 160001141625 |  |  | 160003531625 | [11 empty] | 162004031630 |  |  | 155002611625 |  |  |  | X
195 | 1000000124 | ΥΜΙ 1621 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 |  |  | 2016-09-05 | 2016-09-05 |  | 160004991625 |  |  | 160002931625 |  |  | 160000421625 | [11 empty] | 162005981632 |  |  | 155001251624 |  |  |  | X
196 | 1000000123 | ΥΜΙ 1620 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 |  |  | 2016-09-05 | 2016-09-05 |  | 160000901625 |  |  | 160002221625 |  |  | 160002531625 | [11 empty] | 162003401630 |  |  | 155001211624 |  |  |  | X
197 | 1000000619 | ΖΚΖ 9727 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 |  |  | 2016-09-14 | 2016-09-14 |  | 160005491625 |  |  | 160020391633 |  |  | 160004281625 | [11 empty] | 162002651630 |  |  | 155004351630 |  |  |  | O
198 | 1000000652 | ΖΚΖ 9760 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 |  |  | 2016-09-17 | 2016-09-17 |  | 160008031630 |  |  | 160009291630 |  |  | 160001751625 | [11 empty] | 162004231630 |  |  | 155005471631 |  |  |  | O
199 |  | ΖΚΖ 9762 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 | [30 empty] | X
200 |  | ΖΚΖ 9779 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 | [30 empty] | X
201 |  | ΖΚΖ 9809 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-27 | 2016-07-27 | [30 empty] | X
202 | 1000000131 | ΥΜΙ 1633 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 |  |  | 2016-09-08 | 2016-09-08 |  | 160021081633 |  |  | 160004041625 |  |  | 160002091625 | [11 empty] | 162004541632 |  |  | 155002711625 |  |  |  | X
203 | 1000000130 | ΥΜΙ 1632 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 |  |  | 2016-08-29 | 2016-08-29 |  | 160001271625 |  |  | 160005261625 |  |  | 160004391625 | [11 empty] | 162000261625 |  |  | 155001641624 |  | 2016-09-03 | 2016-09-03 | X
204 | 1000000132 | ΥΜΙ 1634 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 |  |  | 2016-08-22 | 2016-08-22 |  | 160000491625 |  |  | 160005911625 |  |  | 160002121625 | [11 empty] | 162001841625 |  |  | 155002221624 |  |  |  | X
205 | 1000000136 | ΥΜΙ 1640 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 |  |  | 2016-09-09 | 2016-09-09 |  | 160002591625 |  |  | 160004351625 |  |  | 160010961630 | [11 empty] | 162003501630 |  |  | 155003191630 |  |  |  | X
206 | 1000000135 | ΥΜΙ 1639 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 |  |  | 2016-09-07 | 2016-09-07 |  | 160007571630 |  |  | 160009581630 |  |  | 160012651632 | [11 empty] | 162005671632 |  |  | 155001951624 |  |  |  | X
207 | 1000000133 | ΥΜΙ 1635 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 |  |  | 2016-08-22 | 2016-08-22 |  | 160000991625 |  |  | 160001821625 |  |  | 160002391625 | [11 empty] | 162000461625 |  |  | 155002261624 |  | 2016-08-27 | 2016-08-27 | X
208 | 1000000261 | ΥΝΝ 9787 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 |  |  | 2016-09-07 | 2016-09-07 |  | 160008781630 |  |  | 160005371625 | [14 empty] | 162004711632 |  |  | 155002371624 |  | 2016-09-10 | 2016-09-10 | X
209 | 1000000264 | ΥΝΝ 9790 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 |  |  | 2016-09-07 | 2016-09-07 |  | 160016211632 |  |  | 160012861632 | [14 empty] | 162006351632 |  |  | 155000631624 |  | 2016-09-10 | 2016-09-10 | X
210 | 1000000265 | ΥΝΝ 9791 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 |  |  | 2016-09-07 | 2016-09-07 |  | 160012981632 |  |  | 160014161632 | [14 empty] | 162003591630 |  |  | 155002131624 |  |  |  | X
211 | 1000000267 | ΥΝΝ 9795 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 |  |  | 2016-09-07 | 2016-09-07 |  | 160019241633 |  |  | 160004841625 | [14 empty] | 162005541632 |  |  | 155000891624 |  | 2016-09-10 | 2016-09-10 | X
212 | 1000000258 | ΥΝΝ 9784 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 |  |  | 2016-09-06 | 2016-09-06 |  | 160007011630 |  |  | 160018011633 | [14 empty] | 162003351630 |  |  | 155002311624 |  |  |  | X
213 | 1000000257 | ΥΝΝ 9783 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 |  |  | 2016-09-10 | 2016-09-10 |  | 160008171630 |  |  | 160002101625 | [14 empty] | 162000491625 |  |  | 155004461630 |  |  |  | O
214 | 1000000685 | ΖΚΖ 9794 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 |  |  | 2016-09-21 | 2016-09-21 |  | 160006381630 |  |  | 160009201630 |  |  | 160008291630 | [11 empty] | 162003871630 |  |  | 155004231630 |  |  |  | O
215 |  | ΖΚΖ 9822 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 | [30 empty] | X
216 | 1000000638 | ΖΚΖ 9746 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 |  |  | 2016-09-16 | 2016-09-16 |  | 160010301630 |  |  | 160007321630 |  |  | 160009931630 | [11 empty] | 162004401631 |  |  | 155003179630 |  |  |  | X
217 | 1000000663 | ΖΚΖ 9771 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 |  |  | 2016-09-19 | 2016-09-19 |  | 160008501630 |  |  | 160007681630 |  |  | 160006661630 | [11 empty] | 162003611630 |  |  | 155007471632 |  |  |  | O
218 | 1000000661 | ΖΚΖ 9769 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-28 | 2016-07-28 |  |  | 2016-09-19 | 2016-09-19 |  | 160008711630 |  |  | 160007651630 |  |  | 160006121630 | [11 empty] | 162002211630 |  |  | 155005451631 |  |  |  | O
219 | 1000000259 | ΥΝΝ 9785 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 |  |  | 2016-09-06 | 2016-09-06 |  | 160019391633 |  |  | 160019861633 | [14 empty] | 162002321630 |  |  | 155000561624 |  |  |  | X
220 | 1000000268 | ΥΝΝ 9797 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 |  |  | 2016-09-08 | 2016-09-08 |  | 160011261630 |  |  | 160003361625 | [14 empty] | 162006051632 |  |  | 155001751624 |  |  |  | X
221 | 1000000270 | ΥΝΝ 9799 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 |  |  | 2016-09-08 | 2016-09-08 |  | 160008821630 |  |  | 160008751630 | [14 empty] | 162000941625 |  |  | 155001741624 |  | 2016-09-10 | 2016-09-10 | X
222 | 1000000272 | ΥΝΝ 9801 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 |  |  | 2016-09-08 | 2016-09-08 |  | 160010981630 |  |  | 160009471630 | [14 empty] | 162005491632 |  |  | 155002741625 |  |  |  | X
223 | 1000000273 | ΥΝΝ 9802 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 |  |  | 2016-09-05 | 2016-09-05 |  | 160003511625 |  |  | 160002791625 | [14 empty] | 162005011632 |  |  | 155001971624 |  |  |  | X
224 | 1000000274 | ΥΝΝ 9803 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 |  |  | 2016-09-08 | 2016-09-08 |  | 160018311633 |  |  | 160004771625 | [14 empty] | 162001121625 |  |  | 155001991624 |  | 2016-09-10 | 2016-09-10 | X
225 | 1000000275 | ΥΝΝ 9804 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 |  |  | 2016-09-08 | 2016-09-08 |  | 160016921632 |  |  | 160019961633 | [14 empty] | 162006431632 |  |  | 155001911624 |  | 2016-09-10 | 2016-09-10 | X
226 | 1000000276 | ΥΝΝ 9805 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 |  |  | 2016-09-09 | 2016-09-09 |  | 160002671625 |  |  | 160021331633 | [14 empty] | 162003411630 |  |  | 155004871630 |  |  |  | X
227 | 1000000277 | ΥΝΝ 9806 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 |  |  | 2016-09-09 | 2016-09-09 |  | 160002241625 |  |  | 160003091625 | [14 empty] | 162002861630 |  |  | 155003051630 |  |  |  | X
228 | 1000000280 | ΥΝΝ 9809 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 |  |  | 2016-09-09 | 2016-09-09 |  | 160001551625 |  |  | 160005591625 | [14 empty] | 162003071630 |  |  | 155004361630 |  |  |  | X
229 | 1000000004 | ΥΕΚ 5252 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 |  |  | 2016-08-23 | 2016-08-23 |  | 160004370625 |  |  | 160005421625 |  |  | 160005561625 | [11 empty] | 162000611625 |  |  | 155002041624 |  | 2016-09-10 | 2016-09-10 | X
230 | 1000000137 | ΥΜΙ 1641 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 |  |  | 2016-09-08 | 2016-09-08 |  | 160003131625 |  |  | 160011551630 |  |  | 160010291630 | [11 empty] | 16200591625 |  |  | 155001171624 |  |  |  | X
231 | 1000000611 | ΖΚΖ 9718 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 |  |  | 2016-09-13 | 2016-09-13 |  | 160003651625 |  |  | 160003681625 |  |  | 160002001625 | [11 empty] | 162001571625 |  |  | 155003631630 |  |  |  | O
232 |  | ΖΚΖ 9772 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 | [30 empty] | X
233 | 1000000666 | ΖΚΖ 9774 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 |  |  | 2016-09-20 | 2016-09-20 |  | 160009261630 |  |  | 160008581630 |  |  | 160007701630 | [11 empty] | 162003511630 |  |  | 155007801637 |  |  |  | X
234 | 1000000692 | ΖΚΖ 9801 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 |  |  | 2016-09-20 | 2016-09-20 |  | 160009241630 |  |  | 160011101630 |  |  | 160006291630 | [11 empty] | 162005421632 |  |  | 155008591632 |  |  |  | O
235 |  | ΖΚΖ 9825 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-29 | 2016-07-29 | [30 empty] | X
236 | 1000000759 | ΖΚΖ 9868 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-01 | 2016-08-01 |  |  | 2016-09-23 | 2016-09-23 |  | 160009371630 |  |  | 160009551630 |  |  | 160010381630 | [11 empty] | 162004241630 |  |  | 155005111631 |  |  |  | O
237 |  | ΖΚΖ 9867 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-01 | 2016-08-01 | [30 empty] | X
238 | 1000000747 | ΖΚΖ 9856 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-01 | 2016-08-01 |  |  | 2016-09-23 | 2016-09-23 |  | 160011741630 |  |  | 160008201630 |  |  | 160008991630 | [11 empty] | 162006631632 |  |  | 155007671632 |  |  |  | O
239 | 1000000675 | ΖΚΖ 9784 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-01 | 2016-08-01 |  |  | 2016-09-20 | 2016-09-20 |  | 160007491630 |  |  | 160007331630 |  |  | 160010891630 | [11 empty] | 162004141630 |  |  | 155004441630 |  |  |  | O
240 | 1000000750 | ΖΚΖ 9859 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-01 | 2016-08-01 |  |  | 2016-09-23 | 2016-09-23 |  | 160008571630 |  |  | 160008281630 |  |  | 160010171630 | [11 empty] | 162005561632 |  |  | 155008661632 |  |  |  | O
241 |  | ΖΚΖ 9879 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-01 | 2016-08-01 | [30 empty] | X
242 |  | ΖΚΖ 9940 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-01 | 2016-08-01 | [30 empty] | X
243 | 1000000673 | ΖΚΖ 9781 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-01 | 2016-08-01 |  |  | 2016-09-20 | 2016-09-20 |  | 160006421630 |  |  | 160010201630 |  |  | 160010431630 | [11 empty] | 162002971630 |  |  | 155003141630 |  |  |  | O
244 |  | ΖΚΖ 9800 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-01 | 2016-08-01 | [30 empty] | X
245 |  | ΖΚΖ 9780 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-01 | 2016-08-01 | [30 empty] | X
246 | 1000000719 | ΖΚΖ 9828 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-01 | 2016-08-01 |  |  | 2016-09-22 | 2016-09-22 |  | 160008561630 |  |  | 160007251630 |  |  | 160009861630 | [11 empty] | 162001181625 |  |  | 155007651632 |  |  |  | O
247 | 1000000714 | ΖΚΖ 9823 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-01 | 2016-08-01 |  |  | 2016-09-22 | 2016-09-22 |  | 160009341630 |  |  | 160006511630 |  |  | 160010331630 | [11 empty] | 162004651632 |  |  | 155003581630 |  |  |  | O
248 | 1000000755 | ΖΚΖ 9864 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-02 | 2016-08-02 |  |  | 2016-09-23 | 2016-09-23 |  | 160010741630 |  |  | 160011371630 |  |  | 160009071630 | [11 empty] | 162004931632 |  |  | 155007601632 |  |  |  | O
249 | 1000000744 | ΖΚΖ 9853 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-02 | 2016-08-02 |  |  | 2016-09-23 | 2016-09-23 |  | 160008761630 |  |  | 160011711630 |  |  | 160011901630 | [11 empty] | 162006441632 |  |  | 155007731632 |  |  |  | O
250 | 1000000686 | ΖΚΖ 9795 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-02 | 2016-08-02 |  |  | 2016-09-21 | 2016-09-21 |  | 160007431630 |  |  | 160010801630 |  |  | 160009821630 | [11 empty] | 162002761630 |  |  | 155004041630 |  |  |  | O
251 |  | ΖΚΖ 9789 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-02 | 2016-08-02 | [30 empty] | X
252 | 1000000646 | ΖΚΖ 9754 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-02 | 2016-08-02 |  |  | 2016-09-21 | 2016-09-21 |  | 160007001630 |  |  | 160007281630 |  |  | 160011201630 | [11 empty] | 162004261630 |  |  | 155005131631 |  |  |  | O
253 |  | ΖΚΖ 9766 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-02 | 2016-08-02 | [30 empty] | X
254 |  | ΖΚΖ 9770 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-02 | 2016-08-02 | [30 empty] | X
255 | 1000000651 | ΖΚΖ 9759 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-02 | 2016-08-02 |  |  | 2016-09-21 | 2016-09-21 |  | 160011921630 |  |  | 160011391630 |  |  | 160011591630 | [11 empty] | 162005691632 |  |  | 155004961631 |  |  |  | O
256 | 1000000647 | ΖΚΖ 9755 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-02 | 2016-08-02 |  |  | 2016-09-17 | 2016-09-17 |  | 160007091630 |  |  | 160011361630 |  |  | 160010881630 | [11 empty] | 162003131630 |  |  | 155005381631 |  |  |  | O
257 | 1000000642 | ΖΚΖ 9750 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-02 | 2016-08-02 |  |  | 2016-09-17 | 2016-09-17 |  | 160006471630 |  |  | 160008211630 |  |  | 160007671630 | [11 empty] | 162001591625 |  |  | 155003201630 |  |  |  | O
258 | 1000000670 | ΖΚΖ 9778 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-02 | 2016-08-02 |  |  | 2016-09-20 | 2016-09-20 |  | 160007121630 |  |  | 160011751630 |  |  | 160009571630 | [11 empty] | 162002851630 |  |  | 155003511630 |  |  |  | O
259 |  | ΖΚΖ 9749 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-02 | 2016-08-02 | [30 empty] | X
260 | 1000000596 | ΖΚΖ 9703 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-02 | 2016-08-02 |  |  | 2016-09-20 | 2016-09-20 |  | 160008671630 |  |  | 160007211630 |  |  | 160010511630 | [11 empty] | 162004021630 |  |  | 155007281632 |  |  |  | O
261 | 1000000600 | ΖΚΖ 9707 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-02 | 2016-08-02 |  |  | 2016-09-14 | 2016-09-14 |  | 160002041625 |  |  | 160002451625 |  |  | 160005221625 | [11 empty] | 162002441630 |  |  | 155004401630 |  |  |  | O
262 | 1000000607 | ΖΚΖ 9714 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-02 | 2016-08-02 |  |  | 2016-09-13 | 2016-09-13 |  | 160005231625 |  |  | 160010931630 |  |  | 160000791625 | [11 empty] | 162000911625 |  |  | 155005001631 |  |  |  | O
263 | 1000000609 | ΖΚΖ 9716 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-02 | 2016-08-02 |  |  | 2016-09-13 | 2016-09-13 |  | 160001421625 |  |  | 160005351625 |  |  | 160006821630 | [11 empty] | 162001691625 |  |  | 155003571630 |  |  |  | O
264 |  | ΖΚΖ 9951 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-03 | 2016-08-03 | [30 empty] | X
265 |  | ΖΚΖ 9955 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-03 | 2016-08-03 | [30 empty] | X
266 |  | ΖΚΖ 9972 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-03 | 2016-08-03 | [30 empty] | X
267 |  | ΖΚΖ 9927 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-03 | 2016-08-03 | [30 empty] | X
268 |  | ΖΚΖ 9983 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-03 | 2016-08-03 | [30 empty] | X
269 |  | ΖΚΖ 9931 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-03 | 2016-08-03 | [30 empty] | X
270 |  | ΖΚΖ 9970 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-03 | 2016-08-03 | [30 empty] | X
271 | 1000000677 | ΖΚΖ 9786 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-03 | 2016-08-03 |  |  | 2016-09-21 | 2016-09-21 |  | 160011601630 |  |  | 160009871630 |  |  | 160010821630 | [11 empty] | 162002721630 |  |  | 155003721630 |  |  |  | O
272 |  | ΖΚΖ 9829 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-03 | 2016-08-03 | [30 empty] | X
273 |  | ΖΚΖ 9976 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-03 | 2016-08-03 | [30 empty] | X
274 |  | ΖΚΖ 9977 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-03 | 2016-08-03 | [30 empty] | X
275 |  | ΖΚΖ 9978 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-03 | 2016-08-03 | [30 empty] | X
276 |  | ΖΚΖ 9979 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-03 | 2016-08-03 | [30 empty] | X
277 |  | ΖΚΖ 9980 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-03 | 2016-08-03 | [30 empty] | X
278 |  | ΖΚΖ 9981 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-03 | 2016-08-03 | [30 empty] | X
279 |  | ΖΚΖ 9858 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-03 | 2016-08-03 | [30 empty] | X
280 | 1000000688 | ΖΚΖ 9797 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-04 | 2016-08-04 |  |  | 2016-09-21 | 2016-09-21 |  | 160010851630 |  |  | 160006771630 |  |  | 160007931630 | [11 empty] | 162002451630 |  |  | 155007611632 |  |  |  | O
281 |  | ΖΚΖ 9798 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-04 | 2016-08-04 | [30 empty] | X
282 |  | ΖΚΖ 9966 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-04 | 2016-08-04 | [30 empty] | X
283 |  | ΖΚΖ 9967 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-04 | 2016-08-04 | [30 empty] | X
284 |  | ΖΚΖ 9968 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-04 | 2016-08-04 | [30 empty] | X
285 |  | ΖΚΖ 9971 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-04 | 2016-08-04 | [30 empty] | X
286 |  | ΖΚΖ 9973 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-04 | 2016-08-04 | [30 empty] | X
287 |  | ΖΚΖ 9924 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-04 | 2016-08-04 | [30 empty] | X
288 |  | ΖΚΖ 9788 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-04 | 2016-08-04 | [30 empty] | X
289 |  | ΖΚΖ 9905 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-04 | 2016-08-04 | [30 empty] | X
290 |  | ΖΚΖ 9899 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-04 | 2016-08-04 | [30 empty] | X
291 |  | ΖΚΖ 9918 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-04 | 2016-08-04 | [30 empty] | X
292 |  | ΖΚΖ 9917 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-04 | 2016-08-04 | [30 empty] | X
293 |  | ΖΚΖ 9869 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-04 | 2016-08-04 | [30 empty] | X
294 |  | ΖΚΖ 9881 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-04 | 2016-08-04 | [30 empty] | X
295 |  | ΖΚΖ 9852 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-04 | 2016-08-04 | [30 empty] | X
296 |  | ΖΚΖ 9812 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-05 | 2016-08-05 | [30 empty] | X
297 |  | ΖΚΖ 9816 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-05 | 2016-08-05 | [30 empty] | X
298 |  | ΖΚΖ 9843 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-05 | 2016-08-05 | [30 empty] | X
299 |  | ΖΚΖ 9860 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-05 | 2016-08-05 | [30 empty] | X
300 | 1000000746 | ΖΚΖ 9855 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-05 | 2016-08-05 |  |  | 2016-09-19 | 2016-09-19 |  | 160009531630 |  |  | 160011801630 |  |  | 160010471630 | [11 empty] | 162000681625 |  |  | 155008001632 |  |  |  | O
301 |  | ΖΚΖ 9898 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-05 | 2016-08-05 | [30 empty] | X
302 |  | ΖΚΖ 9975 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-05 | 2016-08-05 | [30 empty] | X
303 |  | ΖΚΖ 9939 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-05 | 2016-08-05 | [30 empty] | X
304 |  | ΖΚΖ 9831 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-05 | 2016-08-05 | [30 empty] | X
305 | 1000000690 | ΖΚΖ 9799 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-05 | 2016-08-05 |  |  | 2016-09-14 | 2016-09-14 |  | 160010991630 |  |  | 160005281625 |  |  | 160001451625 | [11 empty] | 162000141625 |  |  | 155005021631 |  |  |  | O
306 |  | ΖΚΖ 9820 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-05 | 2016-08-05 | [30 empty] | X
307 |  | ΖΚΖ 9920 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-05 | 2016-08-05 | [30 empty] | X
308 |  | ΖΚΖ 9850 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-05 | 2016-08-05 | [30 empty] | X
309 | 1000000803 | ΖΚΖ 9914 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-05 | 2016-08-05 |  |  | 2016-09-20 | 2016-09-20 |  | 160011011630 |  |  | 160007621630 |  |  | 160010591630 | [11 empty] | 162003821630 |  |  | 155003251630 |  |  |  | O
310 |  | ΖΚΖ 9896 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-05 | 2016-08-05 | [30 empty] | X
311 | 1000000622 | ΖΚΖ 9730 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-06 | 2016-08-06 |  |  | 2016-09-14 | 2016-09-14 |  | 160005981625 |  |  | 160005501625 |  |  | 160001951625 | [11 empty] | 162001501625 |  |  | 155003271630 |  |  |  | O
312 | 1000000633 | ΖΚΖ 9741 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-06 | 2016-08-06 |  |  | 2016-09-19 | 2016-09-19 |  | 160007481630 |  |  | 160010941630 |  |  | 160006871630 | [11 empty] | 162002961630 |  |  | 155004731630 |  |  |  | O
313 |  | ΖΚΖ 9763 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-06 | 2016-08-06 | [30 empty] | X
314 |  | ΖΚΖ 9915 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-06 | 2016-08-06 | [30 empty] | X
315 | 1000000602 | ΖΚΖ 9709 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-06 | 2016-08-06 |  |  | 2016-09-12 | 2016-09-12 |  | 160003021625 |  |  | 160001481625 |  |  | 160004311625 | [11 empty] | 162000291625 |  |  | 155003611630 |  |  |  | O
316 | 1000000604 | ΖΚΖ 9711 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-06 | 2016-08-06 |  |  | 2016-09-13 | 2016-09-13 |  | 160021031633 |  |  | 160001091625 |  |  | 160001881625 | [11 empty] | 162000921625 |  |  | 155004021630 |  |  |  | O
317 | 1000000606 | ΖΚΖ 9713 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-06 | 2016-08-06 |  |  | 2016-09-13 | 2016-09-13 |  | 160005931625 |  |  | 160001221625 |  |  | 160001101625 | [11 empty] | 162005631632 |  |  | 155003661630 |  |  |  | O
318 | 1000000617 | ΖΚΖ 9725 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-06 | 2016-08-06 |  |  | 2016-09-14 | 2016-09-14 |  | 160004441625 |  |  | 160016551632 |  |  | 160003611625 | [11 empty] | 162000831625 |  |  | 155003711630 |  |  |  | O
319 |  | ΖΚΖ 9873 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-08 | 2016-08-08 | [30 empty] | X
320 |  | ΖΚΖ 9851 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-08 | 2016-08-08 | [30 empty] | X
321 |  | ΖΚΖ 9913 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-08 | 2016-08-08 | [30 empty] | X
322 |  | ΖΚΖ 9911 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-08 | 2016-08-08 | [30 empty] | X
323 |  | ΖΚΖ 9889 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-08 | 2016-08-08 | [30 empty] | X
324 |  | ΖΚΖ 9891 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-08 | 2016-08-08 | [30 empty] | X
325 |  | ΖΚΖ 9811 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-08 | 2016-08-08 | [30 empty] | X
326 | 1000000701 | ΖΚΖ 9810 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-08 | 2016-08-08 |  |  | 2016-09-16 | 2016-09-16 |  | 160011401630 |  |  | 160009211630 |  |  | 160008681630 | [11 empty] | 162004421631 |  |  | 155005031631 |  |  |  | O
327 |  | ΖΚΖ 9803 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-08 | 2016-08-08 | [30 empty] | X
328 |  | ΖΚΖ 9785 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-09 | 2016-08-09 | [30 empty] | X
329 | 1000000634 | ΖΚΖ 9742 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-09 | 2016-08-09 |  |  | 2016-09-19 | 2016-09-19 |  | 160011211630 |  |  | 160010071630 |  |  | 160011051630 | [11 empty] | 162003661630 |  |  | 155005011631 |  |  |  | O
330 |  | ΖΚΖ 9775 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-09 | 2016-08-09 | [30 empty] | X
331 |  | ΖΚΖ 9807 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-09 | 2016-08-09 | [30 empty] | X
332 | 1000000697 | ΖΚΖ 9806 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-09 | 2016-08-09 |  |  | 2016-09-22 | 2016-09-22 |  | 160007311630 |  |  | 160021141633 |  |  | 160011321630 | [11 empty] | 162001701625 |  |  | 155004971631 |  |  |  | O
333 |  | ΖΚΖ 9826 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-09 | 2016-08-09 | [30 empty] | X
334 | 1000000725 | ΖΚΖ 9834 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-09 | 2016-08-09 |  |  | 2016-09-22 | 2016-09-22 |  | 160009491630 |  |  | 160011671630 |  |  | 160011611630 | [11 empty] | 16200521625 |  |  | 155003121630 |  |  |  | O
335 | 1000000724 | ΖΚΖ 9833 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-09 | 2016-08-09 |  |  | 2016-09-22 | 2016-09-22 |  | 160011761630 |  |  | 160010021630 |  |  | 160009101630 | [11 empty] | 162005481632 |  |  | 155003861630 |  |  |  | O
336 | 1000000681 | ΖΚΖ 9790 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-09 | 2016-08-09 |  |  | 2016-09-22 | 2016-09-22 |  | 160011541630 |  |  | 160010151630 |  |  | 160009151630 | [11 empty] | 162003811630 |  |  | 155005141631 |  |  |  | O
337 | 1000000683 | ΖΚΖ 9792 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-09 | 2016-08-09 |  |  | 2016-09-22 | 2016-09-22 |  | 160010211630 |  |  | 160012011630 |  |  | 160011621630 | [11 empty] | 162004171630 |  |  | 155005491631 |  |  |  | O
338 |  | ΖΚΖ 9805 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-09 | 2016-08-09 | [30 empty] | X
339 |  | ΖΚΖ 9817 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-09 | 2016-08-09 | [30 empty] | X
340 |  | ΖΚΖ 9930 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-10 | 2016-08-10 | [30 empty] | X
341 |  | ΖΚΖ 9932 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-10 | 2016-08-10 | [30 empty] | X
342 |  | ΖΚΖ 9933 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-10 | 2016-08-10 | [30 empty] | X
343 |  | ΖΚΖ 9934 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-10 | 2016-08-10 | [30 empty] | X
344 |  | ΖΚΖ 9935 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-10 | 2016-08-10 | [30 empty] | X
345 |  | ΖΚΖ 9969 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-10 | 2016-08-10 | [30 empty] | X
346 | 1000000756 | ΖΚΖ 9865 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-10 | 2016-08-10 |  |  | 2016-09-23 | 2016-09-23 |  | 160006991630 |  |  | 160009951630 |  |  | 160011061630 | [11 empty] | 162004491632 |  |  | 155003831630 |  |  |  | O
347 | 1000000693 | ΖΚΖ 9802 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-10 | 2016-08-10 |  |  | 2016-09-22 | 2016-09-22 |  | 160006391630 |  |  | 160006571630 |  |  | 160011511630 | [11 empty] | 162006131632 |  |  | 155003221630 |  |  |  | O
348 | 1000000615 | ΖΚΖ 9722 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-10 | 2016-08-10 |  |  | 2016-09-14 | 2016-09-14 |  | 160005451625 |  |  | 160004291625 |  |  | 160003411625 | [11 empty] | 162001141625 |  |  | 155005361631 |  |  |  | O
349 |  | ΖΚΖ 9866 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-10 | 2016-08-10 | [30 empty] | X
350 |  | ΖΚΖ 9921 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-10 | 2016-08-10 | [30 empty] | X
351 |  | ΖΚΖ 9813 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-10 | 2016-08-10 | [30 empty] | X
352 |  | ΖΚΖ 9712 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-11 | 2016-08-11 | [30 empty] | X
353 |  | ΖΚΖ 9804 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-11 | 2016-08-11 | [30 empty] | X
354 | 1000000601 | ΖΚΖ 9708 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-11 | 2016-08-11 |  |  | 2016-09-23 | 2016-09-23 |  | 160011941630 |  |  | 160007711630 |  |  | 160008231630 | [11 empty] | 162006651632 |  |  | 155003231630 |  |  |  | O
355 |  | ΖΚΖ 9814 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-11 | 2016-08-11 | [30 empty] | X
356 |  | ΖΚΖ 9837 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-11 | 2016-08-11 | [30 empty] | X
357 |  | ΖΚΖ 9731 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-11 | 2016-08-11 | [30 empty] | X
358 |  | ΖΚΖ 9959 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-11 | 2016-08-11 | [30 empty] | X
359 |  | ΖΚΖ 9861 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-11 | 2016-08-11 | [30 empty] | X
360 | 1000000631 | ΖΚΖ 9739 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-11 | 2016-08-11 |  |  | 2016-09-23 | 2016-09-23 |  | 160011181630 |  |  | 160009231630 |  |  | 160008971630 | [11 empty] | 162003051630 |  |  | 155005041631 |  |  |  | O
361 | 1000000628 | ΖΚΖ 9736 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-11 | 2016-08-11 |  |  | 2016-09-19 | 2016-09-19 |  | 160013691632 |  |  | 160010781630 |  |  | 160011561630 | [11 empty] | 162002961630 |  |  | 155004731630 |  |  |  | O
362 |  | ΖΚΖ 9926 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-11 | 2016-08-11 | [30 empty] | X
363 |  | ΥΝΝ 9676 | Α/Σ ΡΕΝΤΗ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-11 | 2016-08-11 | [30 empty] | X
364 |  | ΥΝΝ 9675 | Α/Σ ΡΕΝΤΗ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-12 | 2016-08-12 | [30 empty] | X
365 |  | ΥΝΝ 9661 | Α/Σ ΡΕΝΤΗ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-12 | 2016-08-12 | [30 empty] | X
366 |  | ΥΝΝ 9663 | Α/Σ ΡΕΝΤΗ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-12 | 2016-08-12 | [30 empty] | X
367 |  | ΥΝΝ 9674 | Α/Σ ΡΕΝΤΗ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-12 | 2016-08-12 | [30 empty] | X
368 |  | ΥΝΝ 9666 | Α/Σ ΡΕΝΤΗ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-12 | 2016-08-12 | [30 empty] | X
369 |  | ΥΝΝ 9670 | Α/Σ ΡΕΝΤΗ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-12 | 2016-08-12 | [30 empty] | X
370 |  | ΥΝΝ 9680 | Α/Σ ΡΕΝΤΗ | SOLARIS (8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-12 | 2016-08-12 | [30 empty] | X
371 |  | ΥΝΝ 9672 | Α/Σ ΡΕΝΤΗ | SOLARIS (MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-16 | 2016-08-16 | [30 empty] | X
372 |  | ΥΝΝ 9673 | Α/Σ ΡΕΝΤΗ | SOLARIS (MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-16 | 2016-08-16 | [30 empty] | X
373 |  | ΥΝΝ 9678 | Α/Σ ΡΕΝΤΗ | SOLARIS (MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-16 | 2016-08-16 | [30 empty] | X
374 |  | ΥΝΝ 9662 | Α/Σ ΡΕΝΤΗ | SOLARIS (MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-16 | 2016-08-16 | [30 empty] | X
375 |  | ΖΚΖ 9962 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-16 | 2016-08-16 | [30 empty] | X
376 |  | ΖΚΖ 9956 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-16 | 2016-08-16 | [30 empty] | X
377 |  | ΖΚΖ 9953 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-16 | 2016-08-16 | [30 empty] | X
378 |  | ΖΚΖ 9848 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-16 | 2016-08-16 | [30 empty] | X
379 |  | ΖΚΖ 9854 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-16 | 2016-08-16 | [30 empty] | X
380 |  | ΖΚΖ 9841 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-16 | 2016-08-16 | [30 empty] | X
381 |  | ΖΚΖ 9857 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-16 | 2016-08-16 | [30 empty] | X
382 |  | ΖΚΖ 9910 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-17 | 2016-08-17 | [30 empty] | X
383 |  | ΖΚΖ 9877 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-17 | 2016-08-17 | [30 empty] | X
384 | 1000000669 | ΖΚΖ 9777 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-17 | 2016-08-17 |  |  | 2016-09-20 | 2016-09-20 |  | 160011481630 |  |  | 160011691630 |  |  | 160011251630 | [11 empty] | 162003231630 |  |  | 155003541630 |  |  |  | O
385 |  | ΖΚΖ 9982 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-17 | 2016-08-17 | [30 empty] | X
386 |  | ΖΚΖ 9886 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-17 | 2016-08-17 | [30 empty] | X
387 |  | ΖΚΖ 9878 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-17 | 2016-08-17 | [30 empty] | X
388 |  | ΖΚΖ 9882 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-17 | 2016-08-17 | [30 empty] | X
389 |  | ΖΚΖ 9880 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-17 | 2016-08-17 | [30 empty] | X
390 |  | ΖΚΖ 9906 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-17 | 2016-08-17 | [30 empty] | X
391 |  | ΖΚΖ 9876 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-17 | 2016-08-17 | [30 empty] | X
392 |  | ΖΚΖ 9875 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-17 | 2016-08-17 | [30 empty] | X
393 |  | ΖΚΖ 9796 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-17 | 2016-08-17 | [30 empty] | X
394 | 1000000684 | ΖΚΖ 9793 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-17 | 2016-08-17 |  |  | 2016-09-21 | 2016-09-21 |  | 160007641630 |  |  | 160006801630 |  |  | 160010751630 | [11 empty] | 162003911630 |  |  | 155004221630 |  |  |  | O
395 |  | ΥΝΝ 9679 | Α/Σ ΡΕΝΤΗ | SOLARIS (MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-18 | 2016-08-18 | [30 empty] | X
396 |  | ΥΝΝ 9677 | Α/Σ ΡΕΝΤΗ | SOLARIS (MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-18 | 2016-08-18 | [30 empty] | X
397 |  | ΥΝΝ 9667 | Α/Σ ΡΕΝΤΗ | SOLARIS (MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-18 | 2016-08-18 | [30 empty] | X
398 |  | ΥΝΝ 9664 | Α/Σ ΡΕΝΤΗ | SOLARIS (MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-18 | 2016-08-18 | [30 empty] | X
399 |  | ΖΚΖ 9874 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-18 | 2016-08-18 | [30 empty] | X
400 |  | ΖΚΖ 9872 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-18 | 2016-08-18 | [30 empty] | X
401 |  | ΖΚΖ 9870 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-18 | 2016-08-18 | [30 empty] | X
402 |  | ΖΚΖ 9883 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-18 | 2016-08-18 | [30 empty] | X
403 | 1000000754 | ΖΚΖ 9863 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-18 | 2016-08-18 |  |  | 2016-09-23 | 2016-09-23 |  | 160009091630 |  |  | 160009791630 |  |  | 160007691630 | [11 empty] | 162001661625 |  |  | 155004341630 |  |  |  | O
404 |  | ΖΚΖ 9840 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-18 | 2016-08-18 | [30 empty] | X
405 | 1000000753 | ΖΚΖ 9862 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-18 | 2016-08-18 |  |  | 2016-09-23 | 2016-09-23 |  | 160011351630 |  |  | 160006811630 |  |  | 160008451630 | [11 empty] | 162000171625 |  |  | 155004181630 |  |  |  | O
406 |  | ΖΚΖ 9844 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-18 | 2016-08-18 | [30 empty] | X
407 | 1000000112 | ΥΜΙ 1600 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-22 | 2016-08-22 |  |  | 2016-09-03 | 2016-09-03 |  | 160009111630 |  |  | 160020061633 |  |  | 160019611633 | [11 empty] | 162006061632 |  |  | 155002121624 |  |  |  | X
408 | 1000000128 | ΥΜΙ 1629 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-22 | 2016-08-22 |  |  | 2016-09-07 | 2016-09-07 |  | 160008871630 |  |  | 160020031633 |  |  | 160007581630 | [11 empty] | 162003211630 |  |  | 155001861624 |  |  |  | X
409 | 1000000097 | ΥΜΙ 1581 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-22 | 2016-08-22 |  |  | 2016-09-02 | 2016-09-02 |  | 160000911625 |  |  | 160001391625 |  |  | 160001171625 | [11 empty] | 162006681632 |  |  | 155001101624 |  |  |  | X
410 | 1000000954 | ΥΜΙ 1478 | Π. ΡΑΛΛΗ | VOLVO B 7 L (18m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-14 | 2016-08-14 |  |  | 2016-08-14 | 2016-08-14 |  | 160001361625 |  |  | 160005311625 |  |  | 160003221625 |  |  | 160000821625 | [8 empty] | 162000651625 |  |  | 155002071624 |  |  |  | X
411 | 1000001105 | ΥΝΝ 9885 | Π. ΡΑΛΛΗ | SOLARIS (18m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-14 | 2016-08-14 |  |  | 2016-08-14 | 2016-08-14 |  | 160002811625 |  |  | 160002251625 |  |  | 160001401625 |  |  | 160004461625 | [8 empty] | 162000161625 |  |  | 155001411624 |  |  |  | X
412 | 1000000180 | ΥΝΝ 9702 | Α/Σ ΒΟΤΑΝΙΚΟΣ | SOLARIS ( 8m MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-06 | 2016-08-06 |  |  | 2016-08-06 | 2016-08-06 |  | 160002871625 |  |  | 160004181625 | [14 empty] | 162000571625 |  |  | 155002681625 |  |  |  | X
413 | 1000000033 | YMI 1307 | Α/Σ ΒΟΤΑΝΙΚΟΣ | NEOPLAN ΕΛΒΟ C 97.N 4007 (MIDI ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-07 | 2016-08-07 |  |  | 2016-08-07 | 2016-08-07 |  | 160001571625 |  |  | 160005941625 | [14 empty] | 162000451625 |  |  | 155002461624 |  | 2016-08-27 | 2016-08-27 | X
414 | 1000000788 | ΖΚΖ 9897 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-10 | 2016-08-10 |  |  | 2016-08-10 | 2016-08-10 |  | 160004201625 |  |  | 160002921625 |  |  | 160001081625 | [11 empty] | 162001521625 |  |  | 155000931624 |  |  |  | X
415 | 1000000005 | ΥΕΚ 5253 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-06 | 2016-08-06 |  |  | 2016-08-06 | 2016-08-06 |  | 160001321625 |  |  | 160003161625 |  |  | 160000561625 | [11 empty] | 162002021625 |  |  | 155001661624 |  |  |  | X
416 | 1000000079 | ΥΜΙ 1554 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-07 | 2016-08-07 |  |  | 2016-08-07 | 2016-08-07 |  | 160000721625 |  |  | 160000661625 |  |  | 160002891625 | [11 empty] | 162001801625 |  |  | 155001041624 |  | 2016-09-10 | 2016-09-10 | X
417 | 1000000159 | ΥΜΙ 1747 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 99.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-06 | 2016-08-06 |  |  | 2016-08-06 | 2016-08-06 |  | 160002781625 |  |  | 160002881625 | [14 empty] | 162001461625 |  |  | 15500150624 |  |  |  | X
418 | 1000001708 | 9009 | ΦΙΛΑΔΕΛΦΕΙΑΣ | TROLLEY NEOPLAN - KIEPE N6221 (18m) |  |  | 2016-08-19 | 2016-08-19 |  |  | 2016-08-19 | 2016-08-19 |  | 160001871625 |  |  | 160001971625 |  |  | 160002151625 |  |  | 160002261625 | [8 empty] | 162002051625 |  |  | 155002791625 |  |  |  | X
419 | 1000001623 | 8002 | ΦΙΛΑΔΕΛΦΕΙΑΣ | TROLLEY NEOPLAN - KIEPE N6216 (12m) |  |  | 2016-08-09 | 2016-08-09 |  |  | 2016-08-09 | 2016-08-09 |  | 160000921625 |  |  | 160000311625 |  |  | 160002911625 | [11 empty] | 162000581625 |  |  | 155000731624 |  |  |  | X
420 | 1000001567 | ΥΝΡ 9143 | ΛΙΟΣΙΩΝ | IRISBUS CITELIS CNG (12m ΦΥΣΙΚΟΥ ΑΕΡΙΟΥ) |  |  | 2016-08-10 | 2016-08-10 |  |  | 2016-08-10 | 2016-08-10 |  | 160002361625 |  |  | 160003791625 |  |  | 160002371625 | [11 empty] | 162000701625 |  |  | 155002391624 |  |  |  | X
421 | 1000000467 | ΥΜΙ 1123 | ΕΛΛΗΝΙΚΟΥ | MRC ΕΛΒΟ C 97.405 GΝ (18m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-12 | 2016-08-12 |  |  | 2016-08-12 | 2016-08-12 |  | 160003891625 |  |  | 160000861625 |  |  | 160005031625 |  |  | 160001201625 | [8 empty] | 162002071625 |  |  | 155000591624 |  |  |  | X
422 | 1000001761 | 7046 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-08-11 | 2016-08-11 |  |  | 2016-08-11 | 2016-08-11 |  | 160002561625 |  |  | 160001121625 |  |  | 160001981625 | [11 empty] | 162000541625 |  |  | 155001431624 |  |  |  | X
423 | 1000001360 | ΥΝΕ 9945 | ΑΝΘΟΥΣΑΣ | IRISBUS AGORA S CNG (12m ΦΥΣΙΚΟΥ ΑΕΡΙΟΥ) |  |  | 2016-08-10 | 2016-08-10 |  |  | 2016-08-10 | 2016-08-10 |  | 160005101625 |  |  | 160002831625 |  |  | 160000441625 | [11 empty] | 162000301625 |  |  | 155002321624 |  |  |  | X
424 | 1000001803 | 6089 | Α/Σ ΡΟΥΦ | TROLLEY NEOPLAN - KIEPE N6014 (12m) |  |  | 2016-08-11 | 2016-08-11 |  |  | 2016-08-11 | 2016-08-11 |  | 160003431625 |  |  | 160001961625 |  |  | 160001241625 | [11 empty] | 162000531625 |  |  | 155001831624 |  |  |  | X
425 | 1000001295 | ΖΖΡ 8978 | ΑΝΘΟΥΣΑΣ | IRISBUS AGORA S CNG (12m ΦΥΣΙΚΟΥ ΑΕΡΙΟΥ) |  |  | 2016-08-14 | 2016-08-14 |  |  | 2016-08-14 | 2016-08-14 |  | 160005011625 |  |  | 160001471625 |  |  | 160000281625 | [11 empty] | 162000231625 |  |  | 155002201624 |  |  |  | X
426 | 3000000001 | ΤΑ10005 | TRAM (Α/Σ ΕΛΛΗΝΙΚΟΥ) | ANSALDO BREDA |  |  | 2016-08-11 | 2016-08-11 |  |  | 2016-08-11 | 2016-08-11 |  | 160003711625 |  |  | 160004601625 |  |  | 160000361625 |  |  | 160004331625 |  |  | 160004611625 |  |  | 160005841625 |  |  | 162001361625 |  | 162000661625 | 155000961624 | 155000981624 |  |  | X
427 | 1000000129 | ΥΜΙ 1630 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-23 | 2016-08-23 |  |  | 2016-09-07 | 2016-09-07 |  | 160015701632 |  |  | 160013541632 |  |  | 160004451625 | [11 empty] | 162002801630 |  |  | 155002361624 |  |  |  | X
428 | 1000000140 | ΥΜΙ 1644 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-23 | 2016-08-23 |  |  | 2016-09-08 | 2016-09-08 |  | 160007891630 |  |  | 160010421630 |  |  | 160021301633 | [11 empty] | 162005051632 |  |  | 155001771624 |  |  |  | X
429 | 1000000139 | ΥΜΙ 1643 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-23 | 2016-08-23 |  |  | 2016-09-08 | 2016-09-08 |  | 160005051625 |  |  | 160005901625 |  |  | 160017311633 | [11 empty] | 162006001632 |  |  | 155000871624 |  |  |  | X
430 | 1000000134 | ΥΜΙ 1636 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-23 | 2016-08-23 |  |  | 2016-09-07 | 2016-09-07 |  | 160014431632 |  |  | 160010791630 |  |  | 160003561625 | [11 empty] | 162005811632 |  |  | 155002811626 |  |  |  | X
431 | 1000000141 | ΥΜΙ 1645 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC ΕΛΒΟ C 97.405 Ν (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-24 | 2016-08-24 |  |  | 2016-08-29 | 2016-08-29 |  | 160001621625 |  |  | 160000651625 |  |  | 160005791625 | [11 empty] | 162000951625 |  |  | 155002341624 |  |  |  | X
432 | 1000000019 | ΥΕΚ 5269 | Α/Σ ΒΟΤΑΝΙΚΟΣ | MRC BENZ O 405 N (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-24 | 2016-08-24 |  |  | 2016-08-29 | 2016-08-29 |  | 160005251625 |  |  | 160001851625 |  |  | 160003321625 | [11 empty] | 162001291625 |  |  | 155001351624 |  | 2016-09-03 | 2016-09-03 | X
433 | 1000001820 | 7008 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-03 | 2016-09-03 |  |  | 2016-09-03 | 2016-09-03 |  | 160013001632 |  |  | 160018791633 |  |  | 160017031632 | [11 empty] | 162004631632 |  |  | 155000621624 |  |  |  | X
434 | 1000001755 | 7018 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-05 | 2016-09-05 |  |  | 2016-09-05 | 2016-09-05 |  | 160018081633 |  |  | 160001511625 |  |  | 160013961632 | [11 empty] | 162005361632 |  |  | 155001961624 |  |  |  | X
435 | 1000001822 | 7012 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-05 | 2016-09-05 |  |  | 2016-09-05 | 2016-09-05 |  | 160012431632 |  |  | 160012281632 |  |  | 160013641632 | [11 empty] | 162006601632 |  |  | 155000831624 |  |  |  | X
436 | 1000001847 | 7088 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-06 | 2016-09-06 |  |  | 2016-09-06 | 2016-09-06 |  | 160006271630 |  |  | 160007951630 |  |  | 160011781630 | [11 empty] | 162002981630 |  |  | 155001031624 |  |  |  | X
437 | 1000001853 | 7099 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-06 | 2016-09-06 |  |  | 2016-09-06 | 2016-09-06 |  | 160008621630 |  |  | 160010481630 |  |  | 160006431630 | [11 empty] | 162002561630 |  |  | 155001471624 |  |  |  | X
438 | 1000001774 | 7083 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-07 | 2016-09-07 |  |  | 2016-09-07 | 2016-09-07 |  | 160010531630 |  |  | 160011111630 |  |  | 160015161632 | [11 empty] | 162004381631 |  |  | 155001461624 |  |  |  | X
439 | 1000001776 | 7087 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-07 | 2016-09-07 |  |  | 2016-09-07 | 2016-09-07 |  | 160021251633 |  |  | 160006611630 |  |  | 160012131632 | [11 empty] | 162003261630 |  |  | 155000781624 |  |  |  | X
440 | 1000001757 | 7029 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-08 | 2016-09-08 |  |  | 2016-09-08 | 2016-09-08 |  | 160006711630 |  |  | 160003121625 |  |  | 160005551625 | [11 empty] | 162005151632 |  |  | 155002761625 |  |  |  | X
441 | 1000001751 | 7002 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-08 | 2016-09-08 |  |  | 2016-09-08 | 2016-09-08 |  | 160003761625 |  |  | 160001461625 |  |  | 160002191625 | [11 empty] | 162005091632 |  |  | 155001931624 |  |  |  | X
442 | 1000001752 | 7004 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-08 | 2016-09-08 |  |  | 2016-09-08 | 2016-09-08 |  | 160003961625 |  |  | 160000771625 |  |  | 160000681625 | [11 empty] | 162005991632 |  |  | 155000951624 |  |  |  | X
443 | 1000001824 | 7021 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-09 | 2016-09-09 |  |  | 2016-09-09 | 2016-09-09 |  | 160011881630 |  |  | 160004931625 |  |  | 160009921630 | [11 empty] | 162002601630 |  |  | 155004271630 |  |  |  | X
444 | 1000001821 | 7009 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-09 | 2016-09-09 |  |  | 2016-09-09 | 2016-09-09 |  | 160001651625 |  |  | 160003571625 |  |  | 160004061625 | [11 empty] | 162003801630 |  |  | 155004411630 |  |  |  | X
445 | 1000001779 | 7100 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-10 | 2016-09-10 |  |  | 2016-09-10 | 2016-09-10 |  | 160000601625 |  |  | 160001541625 |  |  | 160012631632 | [11 empty] | 162005431632 |  |  | 155003701630 |  |  |  | O
446 | 1000001758 | 7034 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-10 | 2016-09-10 |  |  | 2016-09-10 | 2016-09-10 |  | 160014581632 |  |  | 160019111633 |  |  | 160000371625 | [11 empty] | 162002361630 |  |  | 155004761630 |  |  |  | O
447 | 1000001773 | 7082 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-12 | 2016-09-12 |  |  | 2016-09-12 | 2016-09-12 |  | 160002801625 |  |  | 160006311630 |  |  | 160003991625 | [11 empty] | 162000121625 |  |  | 155004101630 |  |  |  | O
448 | 1000001828 | 7031 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-12 | 2016-09-12 |  |  | 2016-09-12 | 2016-09-12 |  | 160003721625 |  |  | 160011811630 |  |  | 160012791632 | [11 empty] | 162002641630 |  |  | 155003501630 |  |  |  | O
449 | 1000001850 | 7094 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-12 | 2016-09-12 |  |  | 2016-09-12 | 2016-09-12 |  | 160001721625 |  |  | 160000501625 |  |  | 160014411632 | [11 empty] | 162001401625 |  |  | 155003891630 |  |  |  | O
450 | 1000001819 | 7005 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-13 | 2016-09-13 |  |  | 2016-09-13 | 2016-09-13 |  | 160005821625 |  |  | 160004941625 |  |  | 160001991625 | [11 empty] | 162000621625 |  |  | 155002881630 |  |  |  | O
451 | 1000001753 | 7010 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-13 | 2016-09-13 |  |  | 2016-09-13 | 2016-09-13 |  | 160003461625 |  |  | 160002401625 |  |  | 160005201625 | [11 empty] | 162000411625 |  |  | 155003041630 |  |  |  | O
452 | 1000001831 | 7037 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-13 | 2016-09-13 |  |  | 2016-09-13 | 2016-09-13 |  | 160004871625 |  |  | 160002651625 |  |  | 160005001625 | [11 empty] | 162000091625 |  |  | 155004481630 |  |  |  | O
453 | 1000001825 | 7022 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-14 | 2016-09-14 |  |  | 2016-09-14 | 2016-09-14 |  | 160005431625 |  |  | 160021291633 |  |  | 160005831625 | [11 empty] | 162002381630 |  |  | 155004741630 |  |  |  | O
454 | 1000001826 | 7027 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-14 | 2016-09-14 |  |  | 2016-09-14 | 2016-09-14 |  | 160004911625 |  |  | 160001181625 |  |  | 160002061625 | [11 empty] | 162003241630 |  |  | 155003311630 |  |  |  | O
455 | 1000001754 | 7014 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-14 | 2016-09-14 |  |  | 2016-09-14 | 2016-09-14 |  | 160004711625 |  |  | 160004861625 |  |  | 160003501625 | [11 empty] | 162003461630 |  |  | 155004991631 |  |  |  | O
456 | 3000000031 | ΤΑ10031 | TRAM (Α/Σ ΕΛΛΗΝΙΚΟΥ) | ANSALDO BREDA |  |  | 2016-09-15 | 2016-09-15 |  |  | 2016-09-15 | 2016-09-15 |  | 160004641625 |  |  | 160011191630 |  |  | 160003541625 |  |  | 160008011630 |  |  | 160001761625 |  |  | 160005701625 |  |  | 162003251630 |  | 162003781630 | 155003681630 | 155003101630 |  |  | O
457 | 1000001833 | 7044 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-15 | 2016-09-15 |  |  | 2016-09-15 | 2016-09-15 |  | 160005091625 |  |  | 160003601625 |  |  | 160001781625 | [11 empty] | 162003741630 |  |  | 155004381630 |  |  |  | O
458 | 1000001764 | 7056 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-15 | 2016-09-15 |  |  | 2016-09-15 | 2016-09-15 |  | 160011341630 |  |  | 160005021625 |  |  | 160011151630 | [11 empty] | 162003331630 |  |  | 155007751632 |  |  |  | O
459 | 1000001766 | 7061 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-15 | 2016-09-15 |  |  | 2016-09-15 | 2016-09-15 |  | 160005741625 |  |  | 160003031625 |  |  | 160005391625 | [11 empty] | 162003191630 |  |  | 155005311631 |  |  |  | O
460 | 1000000640 | ΖΚΖ 9748 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-07-21 | 2016-07-21 |  |  | 2016-09-16 | 2016-09-16 |  | 160009351630 |  |  | 160010321630 |  |  | 160009501630 | [11 empty] | 162002351630 |  |  | 155004821630 |  |  |  | O
461 | 1000001858 | 7111 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-16 | 2016-09-16 |  |  | 2016-09-16 | 2016-09-16 |  | 160006161630 |  |  | 160011441630 |  |  | 160011831630 | [11 empty] | 162004361631 |  |  | 155008631632 |  |  |  | O
462 | 1000001842 | 7076 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-16 | 2016-09-16 |  |  | 2016-09-16 | 2016-09-16 |  | 160008161630 |  |  | 160008591630 |  |  | 160007501630 | [11 empty] | 162004341631 |  |  | 155005211631 |  |  |  | O
463 | 1000001767 | 7065 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-16 | 2016-09-16 |  |  | 2016-09-16 | 2016-09-16 |  | 160009411630 |  |  | 160010911630 |  |  | 160007131630 | [11 empty] | 162003021630 |  |  | 155005091631 |  |  |  | O
464 | 3000000014 | ΤΑ10014 | TRAM (Α/Σ ΕΛΛΗΝΙΚΟΥ) | ANSALDO BREDA |  |  | 2016-09-16 | 2016-09-16 |  |  | 2016-09-16 | 2016-09-16 |  | 160010721630 |  |  | 160000881625 |  |  | 160004191625 |  |  | 160003851625 |  |  | 160004631625 |  |  | 160000521625 |  |  | 162002901630 |  | 162002371630 | 155003331630 | 155004031630 |  |  | O
465 | 1000001760 | 7042 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-17 | 2016-09-17 |  |  | 2016-09-17 | 2016-09-17 |  | 160008061630 |  |  | 160008051630 |  |  | 160008841630 | [11 empty] | 162002581630 |  |  | 155007951632 |  |  |  | O
466 | 1000001834 | 7048 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-17 | 2016-09-17 |  |  | 2016-09-17 | 2016-09-17 |  | 160011871630 |  |  | 160007061630 |  |  | 160008961630 | [11 empty] | 162003851630 |  |  | 155003401630 |  |  |  | O
467 | 1000000632 | ΖΚΖ 9740 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-19 | 2016-08-19 |  |  | 2016-09-19 | 2016-09-19 |  | 160014841632 |  |  | 160007871630 |  |  | 160011451630 | [11 empty] | 162003601630 |  |  | 155008681632 |  |  |  | O
468 | 1000001838 | 7060 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-19 | 2016-09-19 |  |  | 2016-09-19 | 2016-09-19 |  | 160006341630 |  |  | 160008181630 |  |  | 160007111630 | [11 empty] | 162003971630 |  |  | 155004191630 |  |  |  | O
469 | 1000001836 | 7054 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-19 | 2016-09-19 |  |  | 2016-09-19 | 2016-09-19 |  | 160011641630 |  |  | 160011161630 |  |  | 160006621630 | [11 empty] | 162002291630 |  |  | 155003601630 |  |  |  | O
470 | 1000001762 | 7049 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-19 | 2016-09-19 |  |  | 2016-09-19 | 2016-09-19 |  | 160011301630 |  |  | 160009221630 |  |  | 160008041630 | [11 empty] | 162003631630 |  |  | 155004071630 |  |  |  | O
471 | 1000001829 | 7033 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-19 | 2016-09-19 |  |  | 2016-09-19 | 2016-09-19 |  | 160011231630 |  |  | 160008901630 |  |  | 160009311630 | [11 empty] | 162000131625 |  |  | 155004161630 |  |  |  | O
472 | 1000001830 | 7035 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-20 | 2016-09-20 |  |  | 2016-09-20 | 2016-09-20 |  | 160010861630 |  |  | 160011381630 |  |  | 160009741630 | [11 empty] | 162004971632 |  |  | 155008651632 |  |  |  | O
473 | 1000001778 | 7092 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-20 | 2016-09-20 |  |  | 2016-09-20 | 2016-09-20 |  | 160012001630 |  |  | 160007451630 |  |  | 160010541630 | [11 empty] | 162005901632 |  |  | 155003551630 |  |  |  | O
474 | 1000001769 | 7074 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-20 | 2016-09-20 |  |  | 2016-09-20 | 2016-09-20 |  | 160006131630 |  |  | 160000511625 |  |  | 160004531625 | [11 empty] | 162004351631 |  |  | 155004131630 |  |  |  | O
475 | 1000001856 | 7107 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-20 | 2016-09-20 |  |  | 2016-09-20 | 2016-09-20 |  | 160007471630 |  |  | 160006171630 |  |  | 160006101630 | [11 empty] | 162003791630 |  |  | 155005441631 |  |  |  | O
476 | 1000001849 | 7093 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-21 | 2016-09-21 |  |  | 2016-09-21 | 2016-09-21 |  | 160006591630 |  |  | 160010871630 |  |  | 160009141630 | [11 empty] | 162003011630 |  |  | 155007421632 |  |  |  | O
477 | 1000001832 | 7041 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-21 | 2016-09-21 |  |  | 2016-09-21 | 2016-09-21 |  | 160007551630 |  |  | 160010711630 |  |  | 160009361630 | [11 empty] | 162003571630 |  |  | 155005501631 |  |  |  | O
478 | 1000001846 | 7086 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-21 | 2016-09-21 |  |  | 2016-09-21 | 2016-09-21 |  | 160006361630 |  |  | 160008381630 |  |  | 160008071630 | [11 empty] | 162003531630 |  |  | 155005071631 |  |  |  | O
479 | 1000001756 | 7025 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-21 | 2016-09-21 |  |  | 2016-09-21 | 2016-09-21 |  | 160007021630 |  |  | 160006111630 |  |  | 160009891630 | [11 empty] | 162002401630 |  |  | 155003751630 |  |  |  | O
480 | 1000000678 | ΖΚΖ 9787 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-19 | 2016-08-19 |  |  | 2016-09-21 | 2016-09-21 |  | 160008541630 |  |  | 160010311630 |  |  | 160008861630 | [11 empty] | 162003291630 |  |  | 155008571632 |  |  |  | O
481 | 1000000649 | ΖΚΖ 9757 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-19 | 2016-08-19 |  |  | 2016-09-22 | 2016-09-22 |  | 160004341625 |  |  | 160008361630 |  |  | 160011631630 | [11 empty] | 162000471625 |  |  | 155005121631 |  |  |  | O
482 | 1000001839 | 7063 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-22 | 2016-09-22 |  |  | 2016-09-22 | 2016-09-22 |  | 160009941630 |  |  | 160006631630 |  |  | 160011041630 | [11 empty] | 162001531625 |  |  | 155003471630 |  |  |  | O
483 | 1000001780 | 7106 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-22 | 2016-09-22 |  |  | 2016-09-22 | 2016-09-22 |  | 160010681630 |  |  | 160010371630 |  |  | 160007541630 | [11 empty] | 162005501632 |  |  | 155004541630 |  |  |  | O
484 | 1000001775 | 7085 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-22 | 2016-09-22 |  |  | 2016-09-22 | 2016-09-22 |  | 160009781630 |  |  | 160007201630 |  |  | 160010701630 | [11 empty] | 162005511632 |  |  | 155004291630 |  |  |  | O
485 | 1000001777 | 7089 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-22 | 2016-09-22 |  |  | 2016-09-22 | 2016-09-22 |  | 160008191630 |  |  | 160008741630 |  |  | 160006281630 | [11 empty] | 162003381630 |  |  | 155003481630 |  |  |  | O
486 | 1000001841 | 7071 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-23 | 2016-09-23 |  |  | 2016-09-23 | 2016-09-23 |  | 160011171630 |  |  | 160010271630 |  |  | 160011421630 | [11 empty] | 162001921625 |  |  | 155005241631 |  |  |  | O
487 | 1000001852 | 7097 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-23 | 2016-09-23 |  |  | 2016-09-23 | 2016-09-23 |  | 160010831630 |  |  | 160011291630 |  |  | 160007601630 | [11 empty] | 162000741625 |  |  | 155002991630 |  |  |  | O
488 | 1000001851 | 7096 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-23 | 2016-09-23 |  |  | 2016-09-23 | 2016-09-23 |  | 160014601632 |  |  | 160008881630 |  |  | 160018801633 | [11 empty] | 162006381632 |  |  | 155004051630 |  |  |  | O
489 | 1000001772 | 7079 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-23 | 2016-09-23 |  |  | 2016-09-23 | 2016-09-23 |  | 160011221630 |  |  | 160019681633 |  |  | 160010611630 | [11 empty] | 162004911632 |  |  | 155007661632 |  |  |  | O
490 | 1000000842 | ΖΚΖ 9954 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-09-24 | 2016-09-24 |  |  | 2016-09-24 | 2016-09-24 |  | 160011571630 |  |  | 160007441630 |  |  | 160010671630 | [11 empty] | 162003991630 |  |  | 155005431631 |  |  |  | O
491 | 1000000849 | ΖΚΖ 9961 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-20 | 2016-08-20 |  |  | 2016-09-24 | 2016-09-24 |  | 160009251630 |  |  | 160006671630 |  |  | 160019761633 | [11 empty] | 162002311630 |  |  | 155007771632 |  |  |  | O
492 | 1000000846 | ΖΚΖ 9958 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-20 | 2016-08-20 |  |  | 2016-09-24 | 2016-09-24 |  | 160011961630 |  |  | 160010191630 |  |  | 160006781630 | [11 empty] | 162002431630 |  |  | 155005321631 |  |  |  | O
493 | 1000000814 | ΖΚΖ 9925 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-20 | 2016-08-20 |  |  | 2016-09-24 | 2016-09-24 |  | 160009761630 |  |  | 160007921630 |  |  | 160007141630 | [11 empty] | 162004371631 |  |  | 155008301632 |  |  |  | O
494 | 1000000818 | ΖΚΖ 9929 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-20 | 2016-08-20 |  |  | 2016-09-24 | 2016-09-24 |  | 160011681630 |  |  | 160006951630 |  |  | 160008421630 | [11 empty] | 162005791632 |  |  | 155005421631 |  |  |  | O
495 | 1000000845 | ΖΚΖ 9957 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-20 | 2016-08-20 |  |  | 2016-09-24 | 2016-09-24 |  | 160010161630 |  |  | 160008461630 |  |  | 160009841630 | [11 empty] | 162003561630 |  |  | 155005101631 |  |  |  | O
496 | 1000000817 | ΖΚΖ 9928 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-20 | 2016-08-20 |  |  | 2016-09-24 | 2016-09-24 |  | 160007521630 |  |  | 160006241630 |  |  | 160010651630 | [11 empty] | 162002471630 |  |  | 155008291632 |  |  |  | O
497 | 1000001837 | 7059 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-24 | 2016-09-24 |  |  | 2016-09-24 | 2016-09-24 |  | 160010811630 |  |  | 160011491630 |  |  | 160011071630 | [11 empty] | 162004291630 |  |  | 155007621632 |  |  |  | O
498 | 1000001827 | 7028 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-24 | 2016-09-24 |  |  | 2016-09-24 | 2016-09-24 |  | 160012051630 |  |  | 160011701630 |  |  | 160006251630 | [11 empty] | 162002241630 |  |  | 155007561632 |  |  |  | O
499 | 1000001823 | 7019 | Α/Σ ΡΟΥΦ | TROLLEY VANHOOL - ALSTOM A300T (12m) |  |  | 2016-09-24 | 2016-09-24 |  |  | 2016-09-24 | 2016-09-24 |  | 160007771630 |  |  | 160010631630 |  |  | 160010041630 | [11 empty] | 162003731630 |  |  | 155005081631 |  |  |  | O
500 |  | ΖΚΖ 9923 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-20 | 2016-08-20 | [30 empty] | X
501 |  | ΖΚΖ 9964 | Α/Σ ΡΕΝΤΗ | IRISBUS AGORA S (12m ΠΕΤΡΕΛΑΙΟΥ) |  |  | 2016-08-20 | 2016-08-20 | [30 empty] | X
502 | [38 empty] | X
503 | [38 empty] | X
504 | [38 empty] | X
505 | [38 empty] | X
506 | [38 empty] | X
507 | [38 empty] | X
508 | [38 empty] | X
509 | [38 empty] | X
510 | [38 empty] | X
511 | [38 empty] | X
512 | [38 empty] | X
513 | [38 empty] | X
514 | [38 empty] | X
515 | [38 empty] | X
516 | [38 empty] | X
517 | [38 empty] | X
518 | [38 empty] | X
519 | [38 empty] | X
520 | [38 empty] | X
521 | [38 empty] | X
522 | [38 empty] | X
523 | [38 empty] | X
524 | [38 empty] | X
525 | [38 empty] | X
526 | [38 empty] | X
527 | [38 empty] | X
528 | [38 empty] | X
529 | [38 empty] | X
530 | [38 empty] | X
531 | [38 empty] | X
532 | [38 empty] | X
533 | [38 empty] | X
534 | [38 empty] | X
535 | [38 empty] | X
536 | [38 empty] | X
537 | [38 empty] | X
538 | [38 empty] | X
539 | [38 empty] | X
540 | [38 empty] | X
541 | [38 empty] | X
542 | [38 empty] | X
543 | [38 empty] | X
544 | [38 empty] | X
545 | [38 empty] | X
546 | [38 empty] | X
547 | [38 empty] | X
548 | [38 empty] | X
549 | [38 empty] | X
550 | [38 empty] | X
551 | [38 empty] | X
552 | [38 empty] | X
553 | [38 empty] | X
554 | [38 empty] | X
555 | [38 empty] | X
556 | [38 empty] | X
557 | [38 empty] | X
558 | [38 empty] | X
559 | [38 empty] | X
560 | [38 empty] | X
561 | [38 empty] | X
562 | [38 empty] | X
563 | [38 empty] | X
564 | [38 empty] | X
565 | [38 empty] | X
566 | [38 empty] | X
567 | [38 empty] | X
568 | [38 empty] | X
569 | [38 empty] | X
570 | [38 empty] | X
571 | [38 empty] | X
572 | [38 empty] | X
573 | [38 empty] | X
574 | [38 empty] | X
575 | [38 empty] | X
576 | [38 empty] | X
577 | [38 empty] | X
578 | [38 empty] | X
579 | [38 empty] | X
580 | [38 empty] | X
581 | [38 empty] | X
582 | [38 empty] | X
583 | [38 empty] | X
584 | [38 empty] | X
585 | [38 empty] | X
586 | [38 empty] | X
587 | [38 empty] | X
588 | [38 empty] | X
589 | [38 empty] | X
590 | [38 empty] | X
591 | [38 empty] | X
592 | [38 empty] | X
593 | [38 empty] | X
594 | [38 empty] | X
595 | [38 empty] | X
596 | [38 empty] | X
597 | [38 empty] | X
598 | [38 empty] | X
599 | [38 empty] | X
600 | [38 empty] | X
601 | [38 empty] | X
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
1018
1019
1020
1021
1022
1023
1024
1025
1026
1027
1028
1029
1030
1031
1032
1033
1034
1035
1036
1037
1038
1039
1040
1041
1042
1043
1044
1045
1046
1047
1048
1049
1050
1051
1052
1053
1054
1055
1056
1057
1058
1059
1060
1061
1062
1063
1064
1065
1066
1067
1068
1069
1070
1071
1072
1073
1074
1075
1076
1077
1078
1079
1080
1081
1082
1083
1084
1085
1086
1087
1088
1089
1090
1091
1092
1093
1094
1095
1096
1097
1098
1099
1100
1101
1102
1103
1104
1105
1106
1107
1108
1109
1110
1111
1112
1113
1114
1115
1116
1117
1118
1119
1120
1121
1122
1123
1124
1125
1126
1127
1128
1129
1130
1131
1132
1133
1134
1135
1136
1137
1138
1139
1140
1141
1142
1143
1144
1145
1146
1147
1148
1149
1150
1151
1152
1153
1154
1155
1156
1157
1158
1159
1160
1161
1162
1163
1164
1165
1166
1167
1168
1169
1170
1171
1172
1173
1174
1175
1176
1177
1178
1179
1180
1181
1182
1183
1184
1185
1186
1187
1188
1189
1190
1191
1192
1193
1194
1195
1196
1197
1198
1199
1200
1201
1202
1203
1204
1205
1206
1207
1208
1209
1210
1211
1212
1213
1214
1215
1216
1217
1218
1219
1220
1221
1222
1223
1224
1225
1226
1227
1228
1229
1230
1231
1232
1233
1234
1235
1236
1237
1238
1239
1240
1241
1242
1243
1244
1245
1246
1247
1248
1249
1250
1251
1252
1253
1254
1255
1256
1257
1258
1259
1260
1261
1262
1263
1264
1265
1266
1267
1268
1269
1270
1271
1272
1273
1274
1275
1276
1277
1278
1279
1280
1281
1282
1283
1284
1285
1286
1287
1288
1289
1290
1291
1292
1293
1294
1295
1296
1297
1298
1299
1300
1301
1302
1303
1304
1305
1306
1307
1308
1309
1310
1311
1312
1313
1314
1315
1316
1317
1318
1319
1320
1321
1322
1323
1324
1325
1326
1327
1328
1329
1330
1331
1332
1333
1334
1335
1336
1337
1338
1339
1340
1341
1342
1343
1344
1345
1346
1347
1348
1349
1350
1351
1352
1353
1354
1355
1356
1357
1358
1359
1360
1361
1362
1363
1364
1365
1366
1367
1368
1369
1370
1371
1372
1373
1374
1375
1376
1377
1378
1379
1380
1381
1382
1383
1384
1385
1386
1387
1388
1389
1390
1391
1392
1393
1394
1395
1396
1397
1398
1399
1400
1401
1402
1403
1404
1405
1406
1407
1408
1409
1410
1411
1412
1413
1414
1415
1416
1417
1418
1419
1420
1421
1422
1423
1424
1425
1426
1427
1428
1429
1430
1431
1432
1433
1434
1435
1436
1437
1438
1439
1440
1441
1442
1443
1444
1445
1446
1447
1448
1449
1450
1451
1452
1453
1454
1455
1456
1457
1458
1459
1460
1461
1462
1463
1464
1465
1466
1467
1468
1469
1470
1471
1472
1473
1474
1475
1476
1477
1478
1479
1480
1481
1482
1483
1484
1485
1486
1487
1488
1489
1490
1491
1492
1493
1494
1495
1496
1497
1498
1499
1500
1501
1502
1503
1504
1505
1506
1507
1508
1509
1510
1511
1512
1513
1514
1515
1516
1517
1518
1519
1520
1521
1522
1523
1524
1525
1526
1527
1528
1529
1530
1531
1532
1533
1534
1535
1536
1537
1538
1539
1540
1541
1542
1543
1544
1545
1546
1547
1548
1549
1550
1551
1552
1553
1554
1555
1556
1557
1558
1559
1560
1561
1562
1563
1564
1565
1566
1567
1568
1569
1570
1571
1572
1573
1574
1575
1576
1577
1578
1579
1580
1581
1582
1583
1584
1585
1586
1587
1588
1589
1590
1591
1592
1593
1594
1595
1596
1597
1598
1599
1600
1601
1602
1603
1604
1605
1606
1607
1608
1609
1610
1611
1612
1613
1614
1615
1616
1617
1618
1619
1620
1621
1622
1623
1624
1625
1626
1627
1628
1629
1630
1631
1632
1633
1634
1635
1636
1637
1638
1639
1640
1641
1642
1643
1644
1645
1646
1647
1648
1649
1650
1651
1652
1653
1654
1655
1656
1657
1658
1659
1660
1661
1662
1663
1664
1665
1666
1667
1668
1669
1670
1671
1672
1673
1674
1675
1676
1677
1678
1679
1680
1681
1682
1683
1684
1685
1686
1687
1688
1689
1690
1691
1692
1693
1694
1695
1696
1697
1698
1699
1700
1701
1702
1703
1704
1705
1706
1707
1708
1709
1710
1711
1712
1713
1714
1715
1716
1717
1718
1719
1720
1721
1722
1723
1724
1725
1726
1727
1728
1729
1730
1731
1732
1733
1734
1735
1736
1737
1738
1739
1740
1741
1742
1743
1744
1745
1746
1747
1748
1749
1750
1751
1752
1753
1754
1755
1756
1757
1758
1759
1760
1761
1762
1763
1764
1765
1766
1767
1768
1769
1770
1771
1772
1773
1774
1775
1776
1777
1778
1779
1780
1781
1782
1783
1784
1785
1786
1787
1788
1789
1790
1791
1792
1793
1794
1795
1796
1797
1798
1799
1800
1801
1802
1803
1804
1805
1806
1807
1808
1809
1810
1811
1812
1813
1814
1815
1816
1817
1818
1819
1820
1821
1822
1823
1824
1825
1826
1827
1828
1829
1830
1831
1832
1833
1834
1835
1836
1837
1838
1839
1840
1841
1842
1843
1844
1845
1846
1847
1848
1849
1850
1851
1852
1853
1854
1855
1856
1857
1858
1859
1860
1861
1862
1863
1864
1865
1866
1867
1868
1869
1870
1871
1872
1873
1874
1875
1876
1877
1878
1879
1880
1881
1882
1883
1884
1885
1886
1887
1888
1889
1890
1891
1892
1893
1894
1895
1896
1897
1898
1899
1900
1901
1902
1903
1904
1905
1906
1907
1908
1909
1910
1911
1912
1913
1914
1915
1916
1917
1918
1919
1920
1921
1922
1923
1924
1925
1926
1927
1928
1929
1930
1931
1932
1933
1934
1935
1936
1937
1938
1939
1940
1941
1942
1943
1944
1945
1946
1947
1948
1949
1950
1951
1952
1953
1954
1955
1956
1957
1958
1959
1960
1961
1962
1963
1964
1965
1966
1967
1968
1969
1970
1971
1972
1973
1974
1975
1976
1977
1978
1979
1980
1981
1982
1983
1984
1985
1986
1987
1988
1989
1990
1991
1992
1993
1994
1995
1996
1997
1998
1999
2000
2001
2002
2003
2004
2005
2006
2007
2008
2009
2010
2011
2012
2013
2014
2015
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
2026
2027
2028
2029
2030
2031
2032
2033
2034
2035
2036
2037
2038
2039
2040
2041
2042
2043
2044
2045
2046
2047
2048
2049
2050
2051
2052
2053
2054
2055
2056
2057
2058
2059
2060
2061
2062
2063
2064
2065
2066
2067
2068
2069
2070
2071
2072
2073
2074
2075
2076
2077
2078
2079
2080
2081
2082
2083
2084
2085
2086
2087
2088
2089
2090
2091
2092
2093
2094
2095
2096
2097
2098
2099
2100
2101
2102
2103
2104
2105
2106
2107
2108
2109
2110
2111
2112
2113
2114
2115
2116
2117
2118
2119
2120
2121
2122
2123
2124
2125
2126
2127
2128
2129
2130
2131
2132
2133
2134
2135
2136
2137
2138
2139
2140
2141
2142
2143
2144
2145
2146
2147
2148
2149
2150
2151
2152
2153
2154
2155
2156
2157
2158
2159
2160
2161
2162
2163
2164
2165
2166
2167
2168
2169
2170
2171
2172
2173
2174
2175
2176
2177
2178
2179
2180
2181
2182
2183
2184
2185
2186
2187
2188
2189
2190
2191
2192
2193
2194
2195
2196
2197
2198
2199
2200
2201
2202
2203
2204
2205
2206
2207
2208
2209
2210
2211
2212
2213
2214
2215
2216
2217
2218
2219
2220
2221
2222
2223
2224
2225
2226
2227
2228
2229
2230
2231
2232
2233
2234
2235
2236
2237
2238
2239
2240
2241
2242
2243
2244
2245
2246
2247
2248
2249
2250
2251
2252
2253
2254
2255
2256
2257
2258
2259
2260
2261
2262
2263
2264
2265
2266
2267
2268
2269
2270
2271
2272
2273
2274
2275
2276
2277
2278
2279
2280
2281
2282
2283
2284
2285
2286
2287
2288
2289
2290
2291
2292
2293
2294
2295
2296
2297
2298
2299
2300
2301
2302
2303
2304
2305
2306
2307
2308
2309
2310
2311
2312
2313
2314
2315
2316
2317
2318
2319
2320
2321
2322
2323
2324
2325
2326
2327
2328
2329
2330
2331
2332
2333
2334
2335
2336
2337
2338
2339
2340
2341
2342
2343
2344
2345
2346
2347
2348
2349
2350
2351
2352
2353
2354
2355
2356
2357
2358
2359
2360
2361
2362
2363
2364
2365
2366
2367
2368
2369
2370
2371
2372
2373
2374
2375
2376
2377
2378
2379
2380
2381
2382
2383
2384
2385
2386
2387
2388
2389
2390
2391
2392
2393
2394
2395
2396
2397
2398
2399
2400
2401
2402
2403
2404
2405
2406
2407
2408
2409
2410
2411
2412
2413
2414
2415
|  |  | Α/Σ ΒΟΤΑΝΙΚΟΣ | Neoplan Elvo C 97.N 4007
|  |  | ΕΛΛΗΝΙΚΟΥ | Solaris (MIDI Πετρελαίου)
|  |  | Α/Σ ΡΕΝΤΗ | MRC Benz O 405 N
|  |  | Π. ΡΑΛΛΗ | MRC ELVO C 97.405 N
|  |  | ΑΓ. ΔΗΜΗΤΡΙΟΥ | MRC ELVO C 99.405 N
|  |  | ΑΝΘΟΥΣΑΣ | IRISBUS AGORA S
|  |  | ΛΙΟΣΙΩΝ | IRISBUS AGORA S CNG
|  |  | ΦΙΛΑΔΕΛΦΕΙΑΣ | RENAULT AGORA S CNG
|  |  | ΑΤΤΙΚΗΣ | IRISBUS CITELIS CNG
|  |  | Α/Σ ΡΟΥΦ | MRC ELVO C 97.405 GN
|  |  | TRAM (Α/Σ ΕΛΛΗΝΙΚΟΥ) | VOLVO B 7 L
SOLARIS (18m Πετρελαίου)
NEOPLAN - KIEPE N6014 (6000)
VANHOOL - ALSTOM A300T (7000)
NEOPLAN - KIEPE N6216 (8000)
NEOPLAN - KIEPE N6221 (9000)
ANSALDO BREDA

## 07-16
■ Daily Progress Report (Onboard Installation)
NO | Operator | Installer | Category | Total | 2016-07 (July) | [30 empty] | Remark
[5 empty] | 2016-07-01 | 2016-07-02 | 2016-07-03 | 2016-07-04 | 2016-07-05 | 2016-07-06 | 2016-07-07 | 2016-07-08 | 2016-07-09 | 2016-07-10 | 2016-07-11 | 2016-07-12 | 2016-07-13 | 2016-07-14 | 2016-07-15 | 2016-07-16 | 2016-07-17 | 2016-07-18 | 2016-07-19 | 2016-07-20 | 2016-07-21 | 2016-07-22 | 2016-07-23 | 2016-07-24 | 2016-07-25 | 2016-07-26 | 2016-07-27 | 2016-07-28 | 2016-07-29 | 2016-07-30 | 2016-07-31
SUM |  |  | Cabling start | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12 | 14 | 13 | 12 | 8 | 0 | 11 | 15 | 14 | 16 | 16 | 11 | 0 | 15 | 17 | 17 | 17 | 17 | 0 | 0
|  |  | Cabling end | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12 | 14 | 13 | 12 | 8 | 0 | 11 | 15 | 14 | 16 | 16 | 11 | 0 | 15 | 17 | 17 | 17 | 17 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Α/Σ ΒΟΤΑΝΙΚΟΣ | TBD | Cabling start | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12 | 11 | 11 | 9 | 6 | 0 | 8 | 12 | 9 | 13 | 12 | 8 | 0 | 10 | 12 | 12 | 12 | 12 | 0 | 0
|  |  | Cabling end | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12 | 11 | 11 | 9 | 6 | 0 | 8 | 12 | 9 | 13 | 12 | 8 | 0 | 10 | 12 | 12 | 12 | 12 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | ΕΛΛΗΝΙΚΟΥ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Α/Σ ΡΕΝΤΗ | TBD | Cabling start | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 0 | 3 | 3 | 5 | 3 | 4 | 3 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0
|  |  | Cabling end | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 2 | 0 | 3 | 3 | 5 | 3 | 4 | 3 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Π. ΡΑΛΛΗ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ΑΓ. ΔΗΜΗΤΡΙΟΥ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ΑΝΘΟΥΣΑΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ΛΙΟΣΙΩΝ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | ΦΙΛΑΔΕΛΦΕΙΑΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | ΑΤΤΙΚΗΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Α/Σ ΡΟΥΦ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | TRAM (Α/Σ ΕΛΛΗΝΙΚΟΥ) | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 08-16
■ Daily Progress Report (Onboard Installation)
NO | Operator | Installer | Category | Total | 2016-08 (August) | [30 empty] | Remark
[5 empty] | 2016-08-01 | 2016-08-02 | 2016-08-03 | 2016-08-04 | 2016-08-05 | 2016-08-06 | 2016-08-07 | 2016-08-08 | 2016-08-09 | 2016-08-10 | 2016-08-11 | 2016-08-12 | 2016-08-13 | 2016-08-14 | 2016-08-15 | 2016-08-16 | 2016-08-17 | 2016-08-18 | 2016-08-19 | 2016-08-20 | 2016-08-21 | 2016-08-22 | 2016-08-23 | 2016-08-24 | 2016-08-25 | 2016-08-26 | 2016-08-27 | 2016-08-28 | 2016-08-29 | 2016-08-30 | 2016-08-31
SUM |  |  | Cabling start | 208 | 12 | 16 | 16 | 16 | 15 | 11 | 2 | 9 | 13 | 15 | 15 | 8 | 0 | 3 | 0 | 11 | 13 | 12 | 4 | 8 | 0 | 3 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 208 | 12 | 16 | 16 | 16 | 15 | 11 | 2 | 9 | 13 | 15 | 15 | 8 | 0 | 3 | 0 | 11 | 13 | 12 | 4 | 8 | 0 | 3 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 99 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 1 | 3 | 3 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 5 | 7 | 8 | 8 | 8 | 6 | 0 | 12 | 14 | 14
|  |  | Equipment Installation end | 99 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 1 | 3 | 3 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 5 | 7 | 8 | 8 | 8 | 6 | 0 | 12 | 14 | 14
|  |  | IC Confirm | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0
1 | Α/Σ ΒΟΤΑΝΙΚΟΣ | TBD | Cabling start | 14 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 14 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 87 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7 | 8 | 8 | 8 | 6 | 0 | 12 | 14 | 14
|  |  | Equipment Installation end | 87 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7 | 8 | 8 | 8 | 6 | 0 | 12 | 14 | 14
|  |  | IC Confirm | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0
2 | ΕΛΛΗΝΙΚΟΥ | TBD | Cabling start | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Α/Σ ΡΕΝΤΗ | TBD | Cabling start | 183 | 12 | 16 | 16 | 16 | 15 | 8 | 0 | 9 | 12 | 13 | 12 | 7 | 0 | 0 | 0 | 11 | 13 | 12 | 3 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 183 | 12 | 16 | 16 | 16 | 15 | 8 | 0 | 9 | 12 | 13 | 12 | 7 | 0 | 0 | 0 | 11 | 13 | 12 | 3 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Π. ΡΑΛΛΗ | TBD | Cabling start | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ΑΓ. ΔΗΜΗΤΡΙΟΥ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ΑΝΘΟΥΣΑΣ | TBD | Cabling start | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ΛΙΟΣΙΩΝ | TBD | Cabling start | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | ΦΙΛΑΔΕΛΦΕΙΑΣ | TBD | Cabling start | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | ΑΤΤΙΚΗΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Α/Σ ΡΟΥΦ | TBD | Cabling start | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | TRAM (Α/Σ ΕΛΛΗΝΙΚΟΥ) | TBD | Cabling start | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 09-16
■ Daily Progress Report (Onboard Installation)
NO | Operator | Installer | Category | Total | 2016-09 (September) | [29 empty] | Remark
[5 empty] | 2016-09-01 | 2016-09-02 | 2016-09-03 | 2016-09-04 | 2016-09-05 | 2016-09-06 | 2016-09-07 | 2016-09-08 | 2016-09-09 | 2016-09-10 | 2016-09-11 | 2016-09-12 | 2016-09-13 | 2016-09-14 | 2016-09-15 | 2016-09-16 | 2016-09-17 | 2016-09-18 | 2016-09-19 | 2016-09-20 | 2016-09-21 | 2016-09-22 | 2016-09-23 | 2016-09-24 | 2016-09-25 | 2016-09-26 | 2016-09-27 | 2016-09-28 | 2016-09-29 | 2016-09-30
SUM |  |  | Cabling start | 57 | 0 | 0 | 1 | 0 | 2 | 2 | 2 | 3 | 2 | 2 | 0 | 3 | 3 | 3 | 4 | 4 | 2 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 57 | 0 | 0 | 1 | 0 | 2 | 2 | 2 | 3 | 2 | 2 | 0 | 3 | 3 | 3 | 4 | 4 | 2 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 255 | 16 | 16 | 10 | 0 | 14 | 13 | 14 | 15 | 13 | 8 | 0 | 9 | 12 | 13 | 9 | 9 | 7 | 0 | 14 | 14 | 12 | 13 | 14 | 10 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 255 | 16 | 16 | 10 | 0 | 14 | 13 | 14 | 15 | 13 | 8 | 0 | 9 | 12 | 13 | 9 | 9 | 7 | 0 | 14 | 14 | 12 | 13 | 14 | 10 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 59 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Α/Σ ΒΟΤΑΝΙΚΟΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 105 | 16 | 16 | 9 | 0 | 12 | 11 | 12 | 12 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 105 | 16 | 16 | 9 | 0 | 12 | 11 | 12 | 12 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 59 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | ΕΛΛΗΝΙΚΟΥ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Α/Σ ΡΕΝΤΗ | TBD | Cabling start | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 9 | 10 | 5 | 5 | 5 | 0 | 10 | 10 | 8 | 9 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 9 | 10 | 5 | 5 | 5 | 0 | 10 | 10 | 8 | 9 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Π. ΡΑΛΛΗ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ΑΓ. ΔΗΜΗΤΡΙΟΥ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ΑΝΘΟΥΣΑΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ΛΙΟΣΙΩΝ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | ΦΙΛΑΔΕΛΦΕΙΑΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | ΑΤΤΙΚΗΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Α/Σ ΡΟΥΦ | TBD | Cabling start | 54 | 0 | 0 | 1 | 0 | 2 | 2 | 2 | 3 | 2 | 2 | 0 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 54 | 0 | 0 | 1 | 0 | 2 | 2 | 2 | 3 | 2 | 2 | 0 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 54 | 0 | 0 | 1 | 0 | 2 | 2 | 2 | 3 | 2 | 2 | 0 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 54 | 0 | 0 | 1 | 0 | 2 | 2 | 2 | 3 | 2 | 2 | 0 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | TRAM (Α/Σ ΕΛΛΗΝΙΚΟΥ) | TBD | Cabling start | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 10-16
■ Daily Progress Report (Onboard Installation)
NO | Operator | Installer | Category | Total | 2016-10 (October) | [30 empty] | Remark
[5 empty] | 2016-10-01 | 2016-10-02 | 2016-10-03 | 2016-10-04 | 2016-10-05 | 2016-10-06 | 2016-10-07 | 2016-10-08 | 2016-10-09 | 2016-10-10 | 2016-10-11 | 2016-10-12 | 2016-10-13 | 2016-10-14 | 2016-10-15 | 2016-10-16 | 2016-10-17 | 2016-10-18 | 2016-10-19 | 2016-10-20 | 2016-10-21 | 2016-10-22 | 2016-10-23 | 2016-10-24 | 2016-10-25 | 2016-10-26 | 2016-10-27 | 2016-10-28 | 2016-10-29 | 2016-10-30 | 2016-10-31
SUM |  |  | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Α/Σ ΒΟΤΑΝΙΚΟΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | ΕΛΛΗΝΙΚΟΥ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Α/Σ ΡΕΝΤΗ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Π. ΡΑΛΛΗ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ΑΓ. ΔΗΜΗΤΡΙΟΥ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ΑΝΘΟΥΣΑΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ΛΙΟΣΙΩΝ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | ΦΙΛΑΔΕΛΦΕΙΑΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | ΑΤΤΙΚΗΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Α/Σ ΡΟΥΦ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | TRAM (Α/Σ ΕΛΛΗΝΙΚΟΥ) | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 11-16
■ Daily Progress Report (Onboard Installation)
NO | Operator | Installer | Category | Total | 2016-11 (November) | [29 empty] | Remark
[5 empty] | 2016-11-01 | 2016-11-02 | 2016-11-03 | 2016-11-04 | 2016-11-05 | 2016-11-06 | 2016-11-07 | 2016-11-08 | 2016-11-09 | 2016-11-10 | 2016-11-11 | 2016-11-12 | 2016-11-13 | 2016-11-14 | 2016-11-15 | 2016-11-16 | 2016-11-17 | 2016-11-18 | 2016-11-19 | 2016-11-20 | 2016-11-21 | 2016-11-22 | 2016-11-23 | 2016-11-24 | 2016-11-25 | 2016-11-26 | 2016-11-27 | 2016-11-28 | 2016-11-29 | 2016-11-30
SUM |  |  | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Α/Σ ΒΟΤΑΝΙΚΟΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | ΕΛΛΗΝΙΚΟΥ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Α/Σ ΡΕΝΤΗ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Π. ΡΑΛΛΗ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ΑΓ. ΔΗΜΗΤΡΙΟΥ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ΑΝΘΟΥΣΑΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ΛΙΟΣΙΩΝ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | ΦΙΛΑΔΕΛΦΕΙΑΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | ΑΤΤΙΚΗΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Α/Σ ΡΟΥΦ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | TRAM (Α/Σ ΕΛΛΗΝΙΚΟΥ) | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 12-16
■ Daily Progress Report (Onboard Installation)
NO | Operator | Installer | Category | Total | 2016-12 (December) | [30 empty] | Remark
[5 empty] | 2016-12-01 | 2016-12-02 | 2016-12-03 | 2016-12-04 | 2016-12-05 | 2016-12-06 | 2016-12-07 | 2016-12-08 | 2016-12-09 | 2016-12-10 | 2016-12-11 | 2016-12-12 | 2016-12-13 | 2016-12-14 | 2016-12-15 | 2016-12-16 | 2016-12-17 | 2016-12-18 | 2016-12-19 | 2016-12-20 | 2016-12-21 | 2016-12-22 | 2016-12-23 | 2016-12-24 | 2016-12-25 | 2016-12-26 | 2016-12-27 | 2016-12-28 | 2016-12-29 | 2016-12-30 | 2016-12-31
SUM |  |  | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Α/Σ ΒΟΤΑΝΙΚΟΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | ΕΛΛΗΝΙΚΟΥ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Α/Σ ΡΕΝΤΗ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Π. ΡΑΛΛΗ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ΑΓ. ΔΗΜΗΤΡΙΟΥ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ΑΝΘΟΥΣΑΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ΛΙΟΣΙΩΝ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | ΦΙΛΑΔΕΛΦΕΙΑΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | ΑΤΤΙΚΗΣ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Α/Σ ΡΟΥΦ | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | TRAM (Α/Σ ΕΛΛΗΝΙΚΟΥ) | TBD | Cabling start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cabling end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Equipment Installation end | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | IC Confirm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Tram_info
VEHICLE_ID | VEHICLE_NUM | OVMC1 | OVMC2
3000000002 | TA10001 | 220001941 | 220001942
3000000003 | TA10002 | 220001943 | 220001944
3000000004 | TA10003 | 220001945 | 220001946
3000000005 | TA10004 | 220001947 | 220001948
3000000001 | TA10005 | 220001949 | 220001950
3000000006 | TA10006 | 220001951 | 220001952
3000000007 | TA10007 | 220001953 | 220001954
3000000008 | TA10008 | 220001955 | 220001956
3000000009 | TA10009 | 220001957 | 220001958
3000000010 | TA10010 | 220001959 | 220001960
3000000011 | TA10011 | 220001961 | 220001962
3000000012 | TA10012 | 220001963 | 220001964
3000000013 | TA10013 | 220001965 | 220001966
3000000014 | TA10014 | 220001967 | 220001968
3000000015 | TA10015 | 220001969 | 220001970
3000000016 | TA10016 | 220001971 | 220001972
3000000017 | TA10017 | 220001973 | 220001974
3000000018 | TA10018 | 220001975 | 220001976
3000000019 | TA10019 | 220001977 | 220001978
3000000020 | TA10020 | 220001979 | 220001980
3000000021 | TA10021 | 220001981 | 220001982
3000000022 | TA10022 | 220001983 | 220001984
3000000023 | TA10023 | 220001985 | 220001986
3000000024 | TA10024 | 220001987 | 220001988
3000000025 | TA10025 | 220001989 | 220001990
3000000026 | TA10026 | 220001991 | 220001992
3000000027 | TA10027 | 220001993 | 220001994
3000000028 | TA10028 | 220001995 | 220001996
3000000029 | TA10029 | 220001997 | 220001998
3000000030 | TA10030 | 220001999 | 220002000
3000000031 | TA10031 | 220002001 | 220002002
3000000032 | TA10032 | 220002003 | 220002004
3000000033 | TA10033 | 220002005 | 220002006
3000000034 | TA10034 | 220002007 | 220002008
3000000035 | TA10035 | 220002009 | 220002010

## TOTAL VEHICLE OSY
Table 1.
Α/Α | VEHICLE TYPE | DEPOT | Vehicle total number with Telematics
1 | NEOPLAN ΕΛΒΟ C97.N4007 (8Μ MIDI) | VOTANIKOS | 45 | 80 | VOTANIKOS | 294
|  | RENTI | 35
2 | SOLARIS (8Μ MIDI) | VOTANIKOS | 131 | 200 | RENTI | 329
|  | ELLINIKO | 54
|  | RENTI | 15 |  | ELLINIKO | 299
3 | MRC BENZ O 405 N (12m) | VOTANIKOS | 30 | 175
|  | ELLINIKO | 85 |  | AGIO DIMITRIOS | 60
|  | AGIO DIMITRIOS | 60
4 | MRC ΕΛΒΟ C 97.405 Ν (12m) | VOTANIKOS | 74 | 134 | PETROU RALLI | 229
|  | PETROU RALLI | 60
5 | MRC ΕΛΒΟ C 99.405 N (12m) | VOTANIKOS | 14 | 18 | ANTHOUSA | 197
|  | PETROU RALLI | 4
6 | IRISBUS AGORA S (12m) | RENTI | 279 | 279 | ANO LIOSIA | 214
7 | IRISBUS AGORA S CNG (12m ) | ANTHOUSA | 102 | 105
|  | ANO LIOSIA | 3 |  | ROUF | 78
8 | RENAULT AGORA S CNG (12m ΦΥΣΙΚΟΥ ΑΕΡΙΟΥ) | ANTHOUSA | 89 | 108
|  | ANO LIOSIA | 19 |  | ΑΤΤΙΚΗ | 30
9 | IRISBUS CITELIS CNG (12m ΦΥΣΙΚΟΥ ΑΕΡΙΟΥ) | ANO LIOSIA | 192 | 198
|  | ANTHOUSA | 6 |  | NEA FILADELFIA | 128
10 | MRC ΕΛΒΟ C 97.405 GN (18m) | ELLINIKO | 160 | 160
11 | VOLVO B 7 L (18m) | PETROU RALLI | 71 | 71
12 | SOLARIS (18m ΠΕΤΡΕΛΑΙΟΥ) | PETROU RALLI | 94 | 94 |  | 1858
13 | NEOPLAN - KIEPE N6014 (12m) | ROUF | 40 | 40
14 | VANHOOL-ALSTOMA300T (12m) | ΑΤΤΙΚΗ | 30 | 68
|  | ROUF | 38
15 | NEOPLAN - KIEPE N6216 (12m) | NEA FILADELFIA | 77 | 77
16 | NEOPLAN - KIEPE N6221 (18m) | NEA FILADELFIA | 51 | 51
| TOTAL |  | 1858 | 1858

## Pin_exchaged
155005351631 | 155007901632 | 155008311632 | 155008241632 | 155007201632 | 155008321632 | 155005391631 | 155007931632
155007171632 | 155007461632 | 155008391632 | 155007921632 | 155008671632 | 55008091632 | 155008421632 | 155008331632
155007491632 | 155008701633 | 155005181631 | 155007121632 | 155005371631 | 155005431631 | 155007211632 | 155007631632
155008141632 | 155007331632 | 155008511632 | 155007761632 | 155008151632 | 155007371632 | 155008611632 | 155008111632
155007941632 | 155005321631 | 155007741632 | 155007111632 | 155008261632 | 155008201632 | 155007821632 | 155008281632
155007311632 | 155005151631 | 155008431632 | 155007911632 | 155007571632 | 155008021632 | 155007811632 | 155008381632
155008351632 | 155007781632 | 155008081632 | 155008131632 | 155007581632 | 155007061632 | 155008401632 | 155007131632
155007411632 | 155008231632 | 155008161632 | 155007321632 | 155007401632 | 155007251632 | 155008561632 | 155005201631
155005481631 | 155008291632 | 155008051632 | 155007341632 | 155008121632 | 155007501632 | 155008071632 | 155007511632
155005461631 | 155008361632 | 155008551632 | 155007681632 | 155008031632 | 155007691632 | 155007591632 | 155007381632
155008621632 | 155007431632 | 155005401631 | 155007441632 | 155008441632 | 155008271632 | 155008341632
155007161632 | 155007521632 | 155005291631 | 155007241632 | 155007561632 | 155005231631 | 155007981632
155007851632 | 155005161631 | 155008541632 | 155007361632 | 155007391632 | 155007551632 | 155007621632
155007291632 | 155007351632 | 155008471632 | 155008451632 | 155005411631 | 155005271631
155008491632 | 155008301632 | 155007541632 | 155008101632 | 155007881632 | 155007791632
155004981631 | 155005341631 | 155008411632 | 155008711633 | 155007071632 | 155008171632
155005171631 | 155008251632 | 155007481632 | 155007971632 | 155008691632 | 155007091632
155007641632 | 155008181632 | 155008481632 | 155007301632 | 155008601632 | 155007221632
155008061632 | 155008221632 | 155007451632 | 155008531632 | 155008581632 | 155005261631
155007831632 | 155007861632 | 155007871632 | 155007151632 | 155007841632 | 155007101632
OBCH (On-board Communication Hub, G-100 HUB)
155004721630 | 155005191631 | 155004791630 | 155004201630 | 155004151630 | 155004581630 | 155007991632 | 155003731630
155004661630 | 155004421630 | 155004921630 | 155003811630 | 155002891630 | 155004631630 | 155007141632 | 155004001630
155004251630 | 155004781630 | 155008011632 | 155004611630 | 155003461630 | 155004321630 | 155008211632 | 155001711624
155004451630 | 155004551630 | 155004641630 | 155007261632 | 155002961630 | 155004471630 | 155004301630 | 155003031630
155003961630 | 155004371630 | 155003691630 | 155003971630 | 155003881630 | 155007181632 | 155008191632 | 155003801630
155003991630 | 155003351630 | 155003951630 | 155002971630 | 155004991630 | 155004891630 | 155003071630 | 155004941630
155002911630 | 155004701630 | 155004431630 | 155002951630 | 155004601630 | 155007191632 | 155003371630 | 155004771630
155003921630 | 155004171630 | 155003451630 | 155003131630 | 155003771630 | 155004571630 | 155003081630 | 155003011630
155002871630 | 155004521630 | 155003641630 | 155003871630 | 155004261630 | 155004931630 | 155004841630 | 155004281630
155008041632 | 155004561630 | 155003021630 | 155004691630 | 155007271632 | 155008371632 | 155004591630 | 155003781630
155003531630 | 155007081632 | 155004881630 | 155004901630 | 155003761630
155004211630 | 155003841630 | 155007711632 | 155002921630 | 155004671630
155008521632 | 155004681630 | 155003941630 | 155003391630 | 155003111630
155004531630 | 155004331630 | 155003061630 | 155002931630 | 155003381630
155004311630 | 155004711630 | 155007231632 | 155004861630 | 155003091630
155003981630 | 155004621630 | 155004751630 | 155003741630 | 155003651630
155004651630 | 155003931630 | 155004911630 | 155002941630 | 155003161630
155008501632 | 155004511630 | 155002901630 | 155007531632 | 155008461632
155007891632 | 155003491630 | 155004801630 | 155002981630
155004501630 | 155004061630 | 155003151630 | 155003341630
155003571630 | 155004101630 | 155003411630
155003281630 | 155004761630 | 155004391630
155004831630 | 155003891630 | 155003501630
155004131630 | 155004851630 | 155003611630
155004461630 | 155003631630 | 155003701630
155003911630 | 155003661630 | 155004021630
155003361630 | 155002801625 | 155003271630
155003671630 | 155003431630 | 155004161630
155003421630 | 155003261630
155004111630 | 155004141630
OBCH (On-board Communication Hub, G-100 HUB)
155007651632 | 155008651632 | 155008661632 | 155005031631 | 155005361631 | 155003821630 | 155008631632 | 155003851630
155004971631 | 155005421631 | 155004961631 | 155004351630 | 155007281632 | 155005041631 | 155007951632 | 155007771632
155005121631 | 155005101631 | 155007661632 | 155004011630 | 155005331631 | 155005451631 | 155004731630 | 155005081631
155007671632 | 155007611632 | 155005441631 | 155004441630 | 155007421632 | 155003721630 | 155004051630 | 155003511630
155005251631 | 155005001631 | 155008681632 | 155002881630 | 155007731632 | 155004041630 | 155004741630 | 155005501631
155005281631 | 155005011631 | 155003481630 | 155003831630 | 155007801632 | 155003551630 | 155003201630 | 155002991630
155005051631 | 155007471632 | 155003121630 | 155008571632 | 155004341630 | 155004541630 | 155004381630 | 155004811630
155007701632 | 155007961632 | 155003681630 | 155005491631 | 155004231630 | 155003231630 | 155004821630 | 155003141630
155008641632 | 155005111631 | 155007601632 | 155005141631 | 155008001632 | 155003401630 | 155003621630 | 155003751630
155005071631 | 155005131631 | 155004181630 | 155005301631 | 155005241631 | 155008591632 | 155004221630 | 155003541630
155003561630 | 155003291630 | 155005091631 | 155003301630
155004291630 | 155003171630 | 155003311630 | 155003251630
155003581630 | 155003041630 | 155003711630 | 155004071630
155003601630 | 155003791630 | 155005021631 | 155007721632
155003861630 | 155003221630 | 155005061631 | 155004091630
155005211631 | 155005381631 | 155004401630 | 155005471631
155004031630 | 155004481630 | 155003521630 | 155004991631
155003101630 | 155004081630 | 155003441630 | 155005311631
155003331630 | 155007751632 | 155004951630
155003471630 | 155004191630 | 155003001630